## NDC Action Plan
NDC Action Plan (Partnership Plan)
Country: |  | Jordan | Prioritized NDC actions
Period covered: |  | 2019-2021
Date updated: |  | October 2020
i. OBJECTIVE: Transition to a low carbon economy (increased share of renewable energy in total energy mix; upscaling energy efficiency measures in multiple sectors; mitigation of methane emissions) |  |  | ii. OUTPUTS |  | iii. Key Performance Indicators (KPIs) | iv. Baseline | v. Targets |  |  | vi. Lead ministry | vii. Funding requirements (total) | viii. Cost co-share contributed by the lead ministry or institution | ix. Implementing Partner(s) | x. Budget | xi. Status | xii. Relevant concept notes and proposals or strategies | Partner Progress on Implementation and Financing |  |  | Quarterly Implementation Progress
|  |  | Output statement | Status |  |  | Yr 1 2019 | Yr 2 2020 | Yr 3 2021
[17 empty] | Direct linkage | Indirect linkage | Description | Q 3 2020
| Policy, Strategy & Legislation | Governance and coordination mechanisms | Improved energy efficiency legal & institutional framework | ongoing | Improvements in regulation framework of energy efficiency approved |  |  | EE regulation framework approved |  | MEMR-JCI-JCC-MoIT |  |  | Netherlands (RVO / ETF) | EUR 0.5 M | Planned |  | Energy Efficiency & Renewable energy in water sector |  | Under preparation: 2020-2022 (0.5) M EUR  The Netherlands Enterprise Agency (RVO)through the Energy Transition Facility (ETF) supports partner countries with their transition to a more sustainable energy supply. Projects are focused on collaboration at policy level. The project will provide an overview of feasible energy saving measures and renewable energy applications (production and storage) for a selected Wastewater treatment plant and a hydraulic zone of water distribution network in the north of Jordan in cooperation with the YWC. The energy saving measures will be implemented in the selected locations for scaling up. Also such pilot activities for energy saving measures in water sector will be used as input for policy dialogue
[13 empty] | IRENA |  | Planned |  | Through CAEP; IRENA plans to implement Renewables Readiness Assessment for Jordan for assessing the suitability of conditions for the development and deployment of renewable energy, along with the actions required to improve those conditions
| Budgeting and Investment | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rooftop solar PV systems installed in residential buildings | ongoing | Number of rooftop solar PV units installed (5000) | 300 solar PV units | 1000 solar PV units | 2000 solar PV units | 2000 solar PV units | MEMR-JREEEF | 10.5 million JOD |  |  |  | Without support | JREEEF Strategy 2015-2018 Scaling up of an on-going project
[5 empty] | Amount of GHG emissions reduced | [6 empty] | JREEEF: 10%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Solar water heaters installed in residential buildings | ongoing | Number of solar water heaters installed (60,000) | 24,000 SWHs | 20,000 SWHs | 20,000 SWHs | 20,000 SWHs | MEMR-JREEEF | 30 million JOD |  | EU |  | Ongoing | JREEEF Strategy 2015-2018 Scaling up of an on-going project | By the end of the second quarter of 2019, 7 500 additional solar water heaters had been installed in Jordan with EU funding within the Renewable Energy and Energy Efficiency (REEE II) programme.
[5 empty] | Amount of GHG emissions reduced | [6 empty] | 20%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rooftop solar PV systems installed in public school buildings | ongoing | Number of rooftop solar PV units installed (1500) | 130 solar PV units | 500 solar PV units | 500 solar PV units | 500 solar PV units | MEMR-JREEEF | 21 million JOD |  | EU |  | Ongoing | JREEEF Strategy 2015-2018 Scaling up of an on-going project | By the end of the second quarter of 2019, 600 PV rooftop systems had been installed in Jordan with EU funding within the Renewable Energy and Energy Efficiency (REEE II) programme.
[13 empty] | KfW | EUR 16.5 M | Ongoing |  | KFW implementing Energy Efficiency Public Building project consists of a pilot and a roll-out phase. (16.5 M EUR soft loan by KFW) Pilot phase: the installation of Energy Saving Measures in five selected buildings (ministerial building, hospitals, health centre, school) to promote and test different technologies (Completed) Roll-out phase: Energy saving measures in 21 MoPWH buildings, 38 hospitals and health care centres, and in 137 schools.(under implementation
[5 empty] | Amount of GHG emissions reduced | [6 empty] | 10-20%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rooftop solar PV systems installed in houses of worship | ongoing | Number of rooftop solar PV units installed (300) | 250 solar PV units | 100 solar PV units | 100 solar PV units | 100 solar PV units | MEMR-JREEEF-Ministry of Islamic Affairs | 4.2 million JOD |  |  |  | Without support | JREEEF Strategy 2015-2018 Scaling up of an on-going project
[5 empty] | Amount of GHG emissions reduced | [6 empty] | 50%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Energy audits conducted in public buildings | ongoing | Number of energy audits conducted (300) | 20 energy audits | 100 audits | 100 audits | 100 audits | MEMR-JREEEF-Ministry of Public Works and Housing | 300,000 JOD |  |  |  | Without support | JREEEF Strategy 2015-2018; National Energy Efficiency Action Plan (NEEAP)
[5 empty] | Amount of potential KWh savings | [6 empty] | 15%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Residential buildings retrofitted with roof and wall thermal insulation | new | Number of buildings thermally insulated (17,000) |  | 2,000 buildings | 5,000 buildings | 10,000 buildings | MEMR-JREEEF | Roof insulation: 32 M JOD Roof and wall insulation: 80 M JOD |  |  |  | Without support | JREEEF Strategy 2015-2018; National Energy Efficiency Action Plan (NEEAP)
[5 empty] | Area of roof and wall surface thermally insulated | [6 empty] | 10%
Amount of KWh saved
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Energy audits and energy efficiency measures implemented at industrial small and medium enterprises (SMEs) | ongoing | Number of SMEs implementing energy audits and EE measures (150) | 60 SMEs | 50 SMEs | 50 SMEs | 50 SMEs | MEMR-JREEEF-Jordan Chamber of Industry | 105 million JOD | JREEEF: 50% of audit costs + interest up to 350,000 JD | EIB/IKI | EUR 9 M | Planned | National Energy Efficiency Action Plan (NEEAP) |  | Rationalizing energy consumption and raising awareness about long-term financial benefits of EE and RE | EIB implementing project fundedd by IKI with estimated budget 9 M EUR (2019-2030) , the project aim to:  Increased on-lending of the selected Financial Intermediary in Jordan for EE and RE projects.  Enhanced Know-How of selected banks in Jordan regarding the technical and financial aspects of EE & RE technologies and their analytical capacity to evaluate such projects.  Enhanced Know-How of SMEs and Mid-Caps in Jordan regarding the technical and financial aspects of EE & RE technologies and their capacity to develop bankable RE & EE projects.  Achieved energy savings and thus reduced GHG-emissions, especially on the level of local SMEs
[5 empty] | Amount of KWh saved | [6 empty] | Owners: 50% of audit costs + cost of implementation
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Enabling small-scale farmers vulnerable group in the agricultural sector of the use of renewable energy categories. To improve their livelihoods and food security | new | Amount of KWH saved | [9 empty] | Without support
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Old refrigerators replaced with more efficient, energy-labelled refrigerators | new | Number of old refrigerators replaced (3000) | 0 | 1,000 refrigerators | 1,000 refrigerators | 1,000 refrigerators | MEMR-JREEEF-JEPCO-EDCO-IDECO | 3 million JOD |  | Discussions on-going w/ AFD |  | Indicative | National Energy Efficiency Action Plan (NEEAP)
[5 empty] | Amount of KWh saved | 0 | TBD | TBD | TBD |  |  | 10% | Explore co-funding by Montreal Protocol |  | Indicative
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | LED lamp fixtures replacing incandescent and fluorescent lamp fixtures in residential buildings | ongoing | Number of LED lamp replacements (1,150,000) | 150,000 LED lamps | 150,000 LED lamps | 500,000 LED lamps | 500,000 LED lamps | MEMR-JREEEF-JEPCO-EDCO-IDECO | 12 million JOD | Yr1 self-financed |  |  | Without support | National Energy Efficiency Action Plan (NEEAP)
[5 empty] | Amount of KWh saved |  | TBD | TBD | TBD |  |  | Yr2 & Yr3: 10%
Amount of GHG emissions mitigated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | RE systems installed for small-scale poultry and cattle farmers |  | Number of poulty farmer beneficieries (2040) |  | 680 poultry farmers | 680 poultry farmers | 680 poultry farmers | MOA |  |  |  |  | Without support
|  |  |  | new | Number of cattle farmer beneficieries (720) |  | 240 cattle farmers | 240 cattle farmers | 240 cattle farmers | MEMR | 20 million JOD |  |  |  |  | Proposal available
[5 empty] | Amount of GHG emissions mitigated |  |  |  |  | Livestock cooperatives
|  | Private sector investments mobilization | Renewable energy adopted for water pumping, as follows: | new | Share (%) of renewable energy in water sector |  |  |  | Total installed capacity of 183 MW | MWI-MEMR-WAJ-JVA |  |  |  |  | Without support | Pre-feasibility studies completed for all projects
|  |  | Khirbat As-Samra WWTP (100% renewable) |  | 20 MW solar power system installed | [5 empty] | €18.4 million
|  |  | Small to medium-sized WWTPs (100% renewable) |  | 4.5 MW solar power system installed | [5 empty] | €4.9 million
|  |  | From sun rays to water drops |  | 26 MW solar power system installed | [5 empty] | €191.5 million
|  |  | Energy over water reservoirs |  | 15 MW solar power system installed | [5 empty] | €15.5 million
|  |  | In-pipe hydro in Aqaba |  | 2.5 MW solar power system installed | [5 empty] | €7.5 million
|  |  | In-pipe hydro in Sweimeh |  | 1 MW solar power system installed |  |  |  | Raise share of renewable energy in water sector to 10% |  | €4 million
|  |  | Floating PV |  | 50 MW solar power system installed | [5 empty] | €65.5 million
|  |  | Powering the Wadi Al-Arab transmission line |  | 9 MW solar power system installed | [5 empty] | €9.3 million |  | KfW |  |  |  | Reductions of greenhouse gas emissions, through bio digesters |  | KFW implementing Climate Protection in the Waste Water Sector Project The project supports, amongst others, to build two bio-digesters in Central Irbid and Wadi Arab and is exploring to provide further input for the professional management of the plants
|  |  | Al-Aqeb well field PV plant |  | 9 MW solar power system installed | [5 empty] | €9.3 million |  |  |  | Without support
|  |  | Disi Expansion |  | 24 MW solar power system installed | [5 empty] | €26.4 million
|  |  | Azraq solar pumping |  | 15 MW solar power system installed | [5 empty] | €14.1 million
|  |  | Al-Lajjun solar pumping |  | 7 MW solar power system installed | [5 empty] | €7.2 million
|  | Private sector investments mobilization | Energy efficiency measures implemented in the water sector: | new | % reduction in energy consumption |  |  |  | 15% reduction in specific energy consumption | MWI-MEMR-WAJ-JVA |  |  | GIZ |  | Ongoing | Pre-feasibility studies completed for all projects | Indirect reduction of GHG emissions, by reducing non-revenue water and thus unnecessary electricity consumption Providing capacity building through tailored performance improvement programs Direct reduction of water losses in order to adapt to scarcity of resources and impacts of climate change |  |  The global IKI project “Water and Wastewater Companies for Climate Mitigation”, implemented by GIZ, and provides support to reduce GHG emissions from water utilities and increasing Energy Efficiency and Renewable Energy applications. The project has been piloting the whole water cycle assessment approach in Madaba Water Utility / Miyahuna and might be able to arrange in the future building the capacity in applying the assessment tool “Energy Performance and Carbon Emissions Assessment and Monitoring” to other utilities e.g. Ma’aan Governorate wells and Korah District among others.  KfW supports two bio-digesters in Central Irbid and Wadi Arab and is exploring to provide further input for the professional management of the plants, transferring lessons learned from the planned pilot biogas plant at Mu’ta in close cooperation with GIZ. This will also include support for the design and on-the job training for operation.  In addition, German Government support Activities and investments supporting energy efficiency (e.g. pumping stations and wells) and increased use of renewable energies in the water sector.
|  |  | Zai-Dabouq water transmission system + RE |  | Amount of KWh saved |  | 47 GWH saved |  |  |  | €103 million
|  |  | Rehabilitation of pumping stations and well fields |  |  |  | 21 GWH saved |  |  |  | 3.29 million JOD |  | KfW | EUR 50 M | Planned |  |  Reduce energy consumption of rehabilitated infrastructure by at least 15%  Reduce green-house gases by 8000 t CO2/year |  | KFW implementing Energy Efficiency in the Water Sector I / II Phase I: 2014 - Q1 2020 Phase II: 2018 - 2024  Energy-efficient rehabilitation of wells and pump stations (Phase I)  Energy-efficient restructuring and rehabilitation of part of the water network in Balqa 26 million EUR (Phase I) 24 million EUR (Phase II) Reduction of green-house gas emissions by increasing energy efficiency in the water sector as well as realization of electricity and cost savings for WAJ and regional water utilities  Reduce energy consumption of rehabilitated infrastructure by at least 15% (objective)  Reduce green-house gases by 8000 t CO2/year (objective) Energy efficiency measures implemented in the water sector Phase I: Construction activities recently completed Phase II: Construction tender under preparation
Optimization of 26 pressurized transmission lines
|  |  | Improvement of water supply systems in Madaba and Irbid | [7 empty] | Irbid: 21.5 million JOD
|  | Private sector investments mobilization | Hydro pumped storage | new | Developing the pumped storage plant in case that the project has been found as feasible | 0 |  |  |  | Ministry of Energy , private sector, NEPCO | 200MUS$ |  |  |  | Without support | available pre feasibility study implemented by EU
|  | Private sector investments mobilization | Construction of a 100 MWp PV solar power plant (wheeling scheme) to provide power to SMEs | new | Design and construction of PV solar power plant completed |  | Design of solar PV plant completed | Construction of solar PV plant completed | PV solar power plant operated | JCI |  |  | KfW | EUR 48 M | Ongoing |  |  | KFW implemented Energy Supply for Host Communities and Syrian Refugees II project withInstallation of a 46 MW PV plant, wheeling agreements ;Reduction of 26,000 t CO2 yearly. | KFW implemented Energy Supply for Host Communities and Syrian Refugees II project with Installation of a 46 MW PV plant, wheeling agreements; Reduction of 26,000 t CO2 yearly. The project budget estimated 48 million EUR grant ; 44 million EUR German government, 4 million EUR Jordanian government
[10 empty] | MEMR | 70 million JOD | SMEs: 50%
SMEs
|  | Up-scaling business solutions | Construction of concentrated solar power (CSP) units at SMEs for industrial thermal heating purposes | new | Number of CSP installations at SMEs for industrial thermal heating uses (45) |  |  |  |  | JCI |  |  |  |  | Without support
[6 empty] | 0 | 5 CSP units installed | 15 CSP units installed | 25 CSP units installed | SMEs | 25 million JOD | SMEs: 50%
|  | Private sector investments mobilization | Natural gas supply infrastructure installed at SMEs | new | Number of SMEs (30) installing NG supply infrastructure to replace diesel & liquid fuels | 0 |  |  | 10 SMEs | SMEs | 75 million JOD |  |  |  | Without support
|  |  | Phasing out use of diesel and liquid fuels at SMEs |  |  |  | 10 SMEs | 10 SMEs |  |  |  | SMEs: 50%
Amount of GHG emissions reduced
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Access to public transport services increased in Jarash | ongoing | % Increase in use of public transport in Jarash | TBD | % rise in person-km traveled by public transport in Jarash | % rise in person-km traveled by public transport in Jarash | % rise in person-km traveled by public transport in Jarash | MOT |  |  |  |  | Without support
[5 empty] | Quantity of fossil fuel reduced in transport sector |  |  |  |  | Jarash Municipality | [5 empty] | Available
LTRC
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Access to public transport services increased in Irbid and Zarqa centers | new | % Increase in use of public transport in Irbid and Zarqa, | 0 | % rise in person-km traveled by public transport | % rise in person-km traveled by public transport | % rise in person-km traveled by public transport | MOT-Municipalities of the Irbid and zarqa urban centers-LTRC | 20 million JOD | TBD | EBRD |  | Ongoing | Available | EBRD support:  Feasibility study.  Finance to operator: (Purchase of buses, construction of depots, management assistance)
Quantity of fossil fuel reduced in transport sector
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Fostering mobility in Amman through a Bus Rapid Transit (BRT) network | ongoing | Increased use of public transport within Amman & reduction in private vehicle use |  | Construction of infrastructure | Commissioning of BRT in Amman | 48,000 tonnes of CO2 eq/yr mitigated | Greater Amman Municipality (GAM) | $250 million |  | AFD | USD 166 M | Ongoing | Available | AFD support construction of the infrastructures to carry the first public transport network (phase 1) in segregated lane and  Support the selection of the private operator for the BRT.
[5 empty] | Quantity of fossil fuel reduced in transport sector |  |  |  | 315,000 riders/day | MOT |  |  | EBRD |  |  |  | EBRD support GAM: Finance to operator: (Purchase of buses, construction of depots, management assistance).
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Fostering mobility between Amman and Zarqa through a Bus Rapid Transit (BRT) line | new | Increased use of public transport between Amman and Zarqa & reduction in private vehicle use | Designs completed |  |  | TBD | Ministry of Public Works |  |  |  |  | Without support
[7 empty] | TBD | TBD |  | MOT-LTRC | [5 empty] | Available
[5 empty] | Quantity of fossil fuel reduced in transport sector |  |  |  |  | GAM
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Battery-electric passenger vehicles deployed for use in public/government fleets | new | % Fraction of all-electric vehicles in public fleets | Enter no. of current electric vehicles in public fleets | 15% | 30% | 75% | MOT-LTRC-GAM-MEMR-Government ministries-NEPCO |  |  |  |  | Without support
Number of all-electric vehicles in public fleets
Quantity of fossil fuel reduced in transport sector
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Implement and applied ITS in puplic transportation | new | % fraction of buses used ITS | 0 |  | 20% |  | MOT-LTRC- | 6MUS$ |  | MOT-LTRC |  | Without support | Preconcept is available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Solar Powered Electric Bus Fleet Pilot in Karak, Ma’an and Tafeilah Governorates | new | % Fraction of all solar power electric buses in public transport | 0 |  |  | 20% | MOT-LTRC-Southren Jordan-Municipalities-in Ma'an, Karak, Tafilah govornorates | $ 46 million |  |  |  | Without support | Pre concept to GCF available
[5 empty] | Quantity of fossil fuel reduced in transport sector | [6 empty] | 50% | private sector
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Battery-electric buses deployed for use in public transport | new | % Fraction of all-electric buses in public transport | 0 | TBD | TBD | TBD | MOT-LTRC-GAM-MEMR-NEPCO-MoEnv-JEF |  |  |  |  | Without support
[5 empty] | Tot vehicle-kilometers traveled by electric buses | [10 empty] | GCF proposal available
[5 empty] | Quantity of fossil fuel reduced in transport sector | [7 empty] | private sector
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Battery-electric bikes deployed for use by university students | new | Number of students using electric bikes |  | Establishing electric bike standards, bike lanes, finance options | 500 students at one university | 1500 students at two universities | MOT-LTRC-GAM-Municipalities-Universities-Public Security Department | $5 million |  |  |  | Without support
[6 empty] | 0 | [5 empty] | 5%
[5 empty] | Number of electric bikes deployed | 0
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Demonstration-scale geothermal energy plant for heating and cooling designed and constructed | new | Design of geothermal plant completed | Feasibility studies prepared | Geothermal plant design & construction | Geothermal plant design & construction | Geothermal plant commissioned for operation | MEMR-JREEEF-NEPCO | TBD based on the feasibility study |  |  |  | Without support
Geothermal plant constructed
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Energy efficient LED street lighting installed in municipalities | ongoing | Number of traditional street lighting units replaced with LED units (405,000) | 80,000 LED lightd installed | 135,000 LED lightd installed | 135,000 LED lightd installed | 135,000 LED lightd installed | MOMA-MEMR-JREEEF-Municipalities | $70-90 million |  |  |  | Without support | Proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rooftop solar PV systems installed in municipal buildings | ongoing | Number of municipal buildings equipped with solar PV systems (85) | 15 municipal buildings | 50 municipal buildings | 20 municipal buildings | 15 municipal buildings | MOMA-Municipalities |  |  |  |  | Without support
[6 empty] | 30 KWp installed |  |  |  |  | $3 million | 10%
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Green building design principles and practices demonstrated | new | Three 100 m2 green model homes built in multiple Governorates (north, middle, south) | 0 | Plans and designs prepared & approved | Home building completed | Awarness campaign launched | MOMA |  |  |  |  | Without support
|  |  | Construction of 3 green model homes | [11 empty] | Without support
Training delivered
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Retrofitting of homes in accordance with green design principles in five cities | new | Number of houses retrofitted (1000) | 48 housed retrofitted | Retrofit of 300 homes | Retrofit of 300 homes | Retrofit of 400 homes | MoEnv-JEF-JGBC-MOMA | 3.3 million JOD |  |  |  | Without support | Proposal available
[5 empty] | Green design training delivered to local builders | Replication of Green Affordable Homes project | Training to 15 CBOs delivered | Project video prepared | Sustainable practices awareness delivered to 1000 households
|  |  | Disseminating green building methods in local building |  | Sustainable practice awareness delivered to CBOs |  | Training delivered to 25 local builders | Sustainability awareness developed | Knowledge sharing workshop organized | [5 empty] | Without support
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Creating a transition towards sustainable cities in Jordan, characterized by a low-carbon economy, a resilient infrastructure, and new green jobs in urban centers | new | Mitigation of urban GHG emissions |  | Urban mobility | Waste recycling | Community | MOPIC-MOMA-MoEnv-MOT-MEMR-CSBE-JEF |  |  |  |  | Without support
[5 empty] | Implementation of adaptation measures |  | Land use planning | Urban safety | Green jobs |  |  | 50%
[5 empty] | Empowerment of workers w/ green jobs |  | Energy efficiency | Water efficiency | Governance
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Municipal solid waste management measures installed in Toqbol, Irbid, to mitigate methane emissions | new | Upgrade of a municipal solid waste transfer station in Toqbol, Irbid |  |  |  | Upgrade of waste transfer station completed | Ministry of Municipal Affairs | $3.5 million | 10% |  |  | Without support | Available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Landfills rehabilitated to mitigate methane emissions | new | Delivering new sanitary cells in Deir Ala landfill |  |  |  | Rehabilitation of landfills completed | Ministry of Municipal Affairs | $10 million |  |  |  | Without support | Available
[5 empty] | Closure of Al-Homra old dump site | [6 empty] | 10%
Collecting & flaring methane gas from old dump
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | A new municipal solid waste landfill built in Ruweished | new | Conducting feasibility study, technical assistance, and training for a new sanitary landfill |  |  |  | New MSW sanitary landfill constructed | Ministry of Municipal Affairs | $10 million | 10% |  |  | Without support | Available
Construction of a new MSW landfill in Ruweished
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | New waste compactors acquired | new | Delivering a 100 new waste compactors to municipalities |  | 60 waste compactors | 20 waste compactors | 20 waste compactors | Ministry of Municipal Affairs | $10 million | 10% |  |  | Without support
A waste transfer station in Toqbol, Irbid, upgraded
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Climate Protection in the Waste Water Sector | ongoing | Construction of biogas digesters at WWTPs | [7 empty] | KFW | 20 M EUR | Ongoing |  | The project supports, amongst others, to build two bio-digesters in Central Irbid and Wadi Arab and is exploring to provide further input for the professional management of the plants. Further it aims at reducing GHG emissions by enhancing sewage sludge disposal at the WWTP of As Samra.
[5 empty] | • Rehabilitation and expansion of Re-Use WWTPs in Northern Jordan | [9 empty] | Ongoing
[5 empty] | • Building of a Monolandfill (cell 1) next to As Samra WWTP | [9 empty] | Concluded
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Biogas production from municipal solid waste landfill in Tafeilah for electricity and/or thermal energy generation | new | Upgrade of a municipal solid waste landfill in Tafeilah for biogas production |  | Design of landfill upgrade completed & approved | Upgrade of landfill in progress | Upgrade of landfill completed | MoEnv | $23.25 million |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
MOMA
Tafeilah Municipality
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Processing of manure collected from commercial farms in Dhulail Municipality to generate compost and biogas | new | Design and construction of centralized facility for converting manure into energy and compost in Dhulail Municipality |  | Design of facility completed & approved | Construction of facility in progress | Construction of facility completed | MoEnv-MOMA-MOA-JEF | $11.75 million |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
Dhulail Municipality
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Treatment of wastewater coupled with biogas production for energy generation at Dhulail Municipality | new | Design and construction of wastewater treatment plant and associated biogas production unit in Dhulail Municipality |  | Design of WWTP completed & approved | Construction of WWTP in progress | Construction of WWTP completed | WAJ-MWI-MoEnv-MOMA-Dhulail Municipality | $23.5 million |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Capacity to mitigate black carbon (BC) emissions enhanced | new | Inventory of black carbon emissions determined |  | Instruments for measuring BC installed | Data collection and modeling in progress | Inventory baseline of BC emissions determined | MoEnv-MOT | $500,000 |  |  |  | Without support | "BC Mitigatiom" assessment report & concept note available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Application of green building codes demonstrated in public and private buildings | new | Number of buildings using green building codes | 0 | 0 | 3 | 3 | Greater Amman Municipality (GAM) | $2.64m |  | UNDP | 2.64 MUS4 | Ongoing | GAM 2018-2022 Strategy | UNDP is currently implementing a project that aims to promoting low-carbon buildings by application of building energy codes-Implementation of building envelope thermal installation-Introducing water efficient fixtures in 6 demonstration projects-Replacement of traditional street lighting with LED modules
|  |  | Development of two city NAMAs including investment plan for existing and new buildings and street lighting |  | No. of NAMAs ideveloped | 0 | 0 | 0 | 2 |  |  |  | UNDP | [7 empty] | info updated
|  |  | identification and quantification of the effectiveness of different policy and financial de-risking instruments for EE buildings using UNDP’s de-risking methodology |  | Development of De-risking report | 0 | 0 | 0 | 1 | [5 empty] | Without support
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Green retrofit of main GAM buildig and City Hall | new | Increased energy efficiency | 0 | Not available | Not available | Not available | GAM |  |  |  |  | Without support
|  |  | Capacity of GAM staff in green building design, operation, and maintenance developed |  | Reduced water consumption |  |  |  |  | JGBC |  |  |  |  | Without support
[5 empty] | No. of capacity building programs within GAM |  |  |  |  | Jordan Engineers Asso.
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Demonstration of sustainable site planning and management of mixed use development promoting interconnected green space, multi-modal transportation, and clean construction | new | Quality of green goals achieved |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
Achieving livable communities indicators
Amount of public-private investment attrected
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Walkability promoted in Amman | new | Length of sidewalks rehabilited |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
|  |  | Traffic congestion reduced |  | Improved access to people with disabilities | 0 | [8 empty] | Without support
|  |  | Public health improved |  | Cultural shift towards walkability | [9 empty] | Without support
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Expanded MSW disposal capacity at Ghabawi landfill | new | Construction of sanitary cell at Ghabawi landfill |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
Amount of methane emissions mitigated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rehabilitating and upgrading biogas collection system in Ghabawi landfill | new | Building of biogas collection system in cells 4 & 5, and connecting it to existing collection system |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
Amount of methane emissions mitigated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Upgrade of Ain Ghazal solid waste transfer station | new | Solid WTS at Ain Ghazal rehabilitated |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
Amount of methane emissions mitigated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Upgrade of Al-Shaer solid waste transfer station | new | Solid WTS at Al-Shaer rehabilitated |  |  |  |  | Greater Amman Municipality (GAM) |  |  |  |  | Without support
Amount of methane emissions mitigated
| Monitoring and Evaluation (M&E) | Data collection and management | Impacts of energy efficiency & renewable energy deployments measured and verified | new | Plan of action for measurement and verification prepared |  |  |  |  | MEMR-JREEEF | TBD based on scope and type of RE and EE measures applied | 10% | WB |  | Planned | JREEEF Strategy 2015-2018 | Through the CAEP, WB is helping Jordan establish the MRV system. This activity will help improve information quality, as a follow-up of the PMR initiative, through in-depth training of energy sector operators and related institutions on key factors as inputs to the MRV system. |  |  | Development and Implementation of the Monitoring reporting and verification system, completed
[5 empty] | Amount of KWh saved from each energy efficiency & renewable energy project calculated |  | KWh saved | KWh saved | KWh saved
| Capacity Building & Lesson-Learning | Communications | Participation rates in JREEEF renewable energy and energy efficiency funding programs increased | new | Number of applicants to JREEEF renewable and energy efficiency programs (e.g., rooftop solar PV, solar water heaters, roof insulation, etc) | TBD | 30% of target audience | 50% of target audience | 70-100% of target audience | MEMR- JREEEF |  |  |  |  | Without support | JREEEF Strategy 2015-2018
TBD
|  | Training needs in any of the other areas/sections | Industrial SMEs certified in ISO 50001 | new | Number of industrial SMEs approved for ISO 50001 certification |  |  |  |  | MEMR- JREEEF-Jordan Chamber of Industry | TBD based on scope |  |  |  | Without support
[6 empty] | 0 | 50 | 50 | 50 |  |  | TBD
|  | Training needs in any of the other areas/sections | Energy management training delivered to municipality managers | new | Number of energy management training workshops conducted for municipality managers | 0 |  |  |  | MOMA-JREEEF-Municipalities |  | TBD |  |  | Without support
|  |  | Adoption of energy efficiency measures and renewable energy systems by municipal managers |  | Number of RE and/or EE programs adopted by municipality managers | 0
|  | Feasibility studies (social, technical, economic) | Feasibility study (technical and economic) for utilizing geothermal energy for heating and cooling purposes for different sectors completed | new |  | Geological data available |  |  | Feasibility study approved | MEMR- JREEEF-NEPCO | 500,000 JOD |  |  |  | Without support
Feasibility study completed and approved
|  | Feasibility studies (social, technical, economic) | Feasibility study of recycling food waste effluents generated by food manufacturers conducted | new |  |  | Feasibility study approved |  |  | Jordan Chamber of Industry (JCI) |  |  |  |  | Without support
[5 empty] | Feasibility study completed & approved | [5 empty] | 15,000 JOD | 5%
SMEs in food industry
|  | Feasibility studies (social, technical, economic) | Feasibility of biogas production from municipal solid waste landfill in Tafeilah for energy generation conducted | new |  |  | Feasibility study completed & approved |  |  | MoEnv-MOMA-Tafeilah Municipality |  |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
[5 empty] | Feasibility study completed and approved | [5 empty] | $2 million
|  | Feasibility study completed and approved | Feasibility of processing manure collected from commercial farms in Dhulail Municipality to generate compost and biogas conducted | new |  |  | Feasibility study completed & approved |  |  | MoEnv-MOMA-MOA-Dhulail Municipality |  |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
[5 empty] | Feasibility study completed and approved | [5 empty] | $1 million
|  | Feasibility studies (social, technical, economic) | Feasibility of treating wastewater coupled with biogas production for energy generation at Dhulail Municipality conducted | new |  |  | Feasibility study completed & approved |  |  | WAJ-MWI-MoEnv-MOMA-Dhulail Municipality |  |  |  |  | Without support | "Methane Mitigation" report and pre-proposal available
[5 empty] | Feasibility study completed and approved | [5 empty] | $2 million
|  | Feasibility studies (social, technical, economic) | Renewable energy assessments conducted for SMEs | ongoing | Number of renewable energy assessments for SMEs conducted |  |  |  |  | Jordan Chamber of Industry |  |  |  |  | Without support | Scaling up of an on-going project
[7 empty] | 50 assessments | 50 assessments | 50 assessments |  | 60,000 JOD | 25%
SMEs
|  | Feasibility studies (social, technical, economic) | National Environmental Impact Assessment (EIA) of switching from diesel fuel to natural gas (NG) conducted | new | Environmental impact assessment (EIA) conducted & approved |  |  |  |  | Jordan Chamber of Industry |  |  |  |  | Without support
[7 empty] | EIA approved |  |  |  | 50,000 JOD | 15%
SMEs
|  | Feasibility studies (social, technical, economic) | Feasibility study of solar wall technology for industrial applications at SMEs conducted | new | Feasibility study conducted & approved |  | Feasibility study completed & approved |  |  | Jordan Chamber of Industry |  |  |  |  | Without support
SMEs
|  | Communications | Awareness of RE & EE applications & benefits targeting industrial SMEs raised | new | Number of SMEs attending RE & EE awareness raising campaign events (1050) | 0 | 300 SMEs | 350 SMEs | 400 SMEs | JCI |  |  |  |  | Without support
[10 empty] | Local chambers of industry | 225,000 JOD | 5% + In-kind
[5 empty] | Number of campaign events held (36) | 0 | 12 events | 12 events | 12 events | JIEC
|  | Training needs in any of the other areas/sections | Energy managers at industrial SMEs qualified for certification in energy management | new | Number of energy managers certified (150) |  | 50 managers | 50 managers | 50 managers | Jordan Chamber of Industry |  |  |  |  | Without support
[11 empty] | 75,000 JOD | SMEs: 20%
|  |  | Faster adoption of EE & RE measures at industrial SMEs |  | Number of EE & RE measures adopted |  | TBD | TBD | TBD | SMEs
|  | Communications | General student population informed about climate change mitigation and adaptation action | new | No. of training courses targeting teachers (100) | 0 | 50 training courses | 50 training courses |  | GAM |  |  |  |  | Without support
[5 empty] | Number of school events (100) | 0 | 50 school events | 50 school events |  | Ministry of Education | 50,000 JOD
|  |  | Capacity of education sector to address climate change raised |  | Number of awarteness events at schools | 0 | Two movies made | Park rehabilitation
ii. OBJECTIVE: Adaptation to climate change strengthened in the water and agricultural sectors |  |  | OUTPUTS |  | iii. Key Performance Indicators (KPIs) | iv. Baseline | v. Targets |  |  | vi. Lead ministry | vii. Funding requirements (total) | viii. Cost co-share contributed by the lead ministry or institution | ix. Implementing Partner(s) | x. Budget | xi. Status | xii. Relevant concept notes and proposals or strategies
|  |  | Output statement | Status |  |  | Yr 1 2019 | Yr 2 2020 | Yr 3 2021
| Budgeting and Investment | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Municipal water distribution network in Ayna, Karak Governorate, rehabilitated | new | % rise in efficiency of distribution network | Current efficiency | TBD | TBD | TBD | MWI-WAJ-Water companies | $5.7 million |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[7 empty] | TBD | TBD | TBD
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Municipal water distribution network in Faqou'a, Karak Governorate, rehabilitated | new | % rise in efficiency of distribution network | Current efficiency | TBD | TBD | TBD | MWI-WAJ-Water companies | $4.3 million |  |  |  |  | Water Sector Capital Investment Program 2016-2025
[7 empty] | TBD | TBD | TBD
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Irrigation distribution network in Northern section of the Al-Aghwar rehabilitated | new | % rise in efficiency of irrigation network | Current efficiency |  | Efficiency of irrigation network raised to 85% |  | MWI-JVA | $8.5 million |  | KfW | EUR 48 M | Ongoing | Water Sector Capital Investment Program 2016-2025 | Irrigation distribution network in Northern section of the Al-Aghwar rehabilitated |  | KFW implementing Adaptation to Climate Change I and II project during 2016 – 2024, the project activities including:  Rehabilitation of Southern, the Northern and the North East Ghors (45 Mil. EUR)  Consultancy services for farmers and Water Users associations (3 Mil. EUR) 48 Mil EUR The main objective of the project is to contribute to the mitigation of climate change risks. The aim is to reduce the vulnerability of farming communities in the Jordan Valley to the impact of climate change through improved supply of irrigation water by decreasing the use of freshwater resources and increasing the use of reclaimed water in the farms and thus saving valuable freshwater resources. In addition, the reduction in the use of fresh water resources for irrigation will make available a significant amount of fresh water for drinking water supply in urban areas such as Amman and Irbid.
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Irrigation distribution network in the mid section of Al-Aghwar rehabilitated | new | % rise in efficiency of irrigation network | Current efficiency |  | Efficiency of irrigation network raised to 85% |  | MWI-JVA | $11.3 million |  | KfW | EUR 24 M | Planned | Water Sector Capital Investment Program 2016-2025 | Irrigation distribution network in the mid section of Al-Aghwar rehabilitated; Pre-feasibility study process |  | KFW implementing Adaptation to Climate Change III (DKTI) during 2020 – 2026 focusing on  Rehabilitation of Middle Ghors with estimated budget 24 M EUR The main objective of the project is to contribute to the mitigation of climate change risks. The aim is to reduce the vulnerability of farming communities in the Jordan Valley to the impact of climate change through improved supply of irrigation water by decreasing the use of freshwater resources and increasing the use of reclaimed water in the farms and thus saving valuable freshwater resources. In addition, the reduction in the use of fresh water resources for irrigation will make available a significant amount of fresh water for drinking water supply in urban areas such as Amman and Irbid.  Saving freshwater by rehabilitation of irrigation networks  Strengthening farmers climate resilience by reliable water supply Irrigation distribution network in the mid section of Al-Aghwar rehabilitated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Irrigation distribution network in the Northeastern section of Al-Aghwar rehabilitated | new | % rise in efficiency of irrigation network | Current efficiency |  | Efficiency of irrigation network raised to 85% |  | MWI-JVA | $8.5 million |  | KfW | EUR 48 M (part of same project as budget above) | Ongoing | Water Sector Capital Investment Program 2016-2025 | Irrigation distribution network in the Northeastern section of Al-Aghwar rehabilitated |  | KFW implementing Adaptation to Climate Change I and II project during 2016 – 2024, the project activities including:  Rehabilitation of Southern, the Northern and the North East Ghors (45 Mil. EUR)  Consultancy services for farmers and Water Users associations (3 Mil. EUR) 48 Mil EUR The main objective of the project is to contribute to the mitigation of climate change risks. The aim is to reduce the vulnerability of farming communities in the Jordan Valley to the impact of climate change through improved supply of irrigation water by decreasing the use of freshwater resources and increasing the use of reclaimed water in the farms and thus saving valuable freshwater resources. In addition, the reduction in the use of fresh water resources for irrigation will make available a significant amount of fresh water for drinking water supply in urban areas such as Amman and Irbid.
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Increased capacity in Balqa'a Governorate to collect and treat wastewater in a region that is not servced with water sanitation services | new | WWTP in Balqa'a designed and built |  |  |  | WWTP built by 2023 |  |  |  | EC | EUR 14.8 M | Planned |  | The European Commission is co-financing with an additional grant of EUR 14.8 million the construction of a Waste Water Treatment Plant in Balqua
[5 empty] | Coverage (%) of wastewater service |  |  |  |  | MWI-WAJ | €115 million |  | AFD, co-financed by GCF |  |  | Concept note available | AFD, co-financed by GCF
Treated wastewater (%) reused
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Expansion of Wadi Hassan WWTP and wastewater network serving municipality of Al-Jnaid and North Jarash | ongoing | Coverage (%) of wastewater service |  | Piloting A decentralized WWTP in Finan Eco-lodges | Piloting environmentally friendly and low-maintenance treatment of sewage sludge at Wadi Hassan WWTP |  | MWI- WAJ | 6.5 M EUR |  | GIZ |  |  | Feasibility studies completed |  Piloting A decentralized WWTP in Finan Eco-lodges  Piloting environmentally friendly and low-maintenance treatment of sewage sludge at Wadi Hassan WWTP |  | GIZ implemented Decentralized Wastewater Management for Adaptation to Climate Change, ACC The project supports the MWI and WAJ in developing and implementing strategies for decentralized wastewater treatment and reuse as a measure for climate change adaptation. In addition, the project carries out various capacity development measures to enhance the expertise, skills and performance in the wastewater sector.
[5 empty] | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 25 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Construction of WWTP and wastewater network serving district of Al-Koura |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 38 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Expansion of Al-Ramtha WWTP and wastewater network serving municipality of Sahl Houran and city of Al-Ramtha |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 38 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) |  |  | Coverage (%) of wastewater service | [7 empty] | KfW | EUR 45 M | Planned | Feasibility studies completed | Construction of wastewater networks in Naour |  | KFW implementing Water Resources Management Programme V project during 2019 - 2025, the main activities:  Expansion of wastewater networks in Al Karak  Expansion of wastewater networks in South Amman with estimated budget 45 Mil. EUR, currently Tendering process
|  |  | Construction of wastewater networks in Naour | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 22 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) |  |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  | Construction of wastewater networks in Madaba | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 45 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) |  |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  | Construction of wastewater networks in Al-Azraq | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 15 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) |  |  | Coverage (%) of wastewater service | [7 empty] | KfW | EUR 48 M (part of same project as budget above) | Planned | Feasibility studies completed | Save freshwater resources through the provision of treated wastewater for irrigation systems  Improving the energy efficiency of the wastewater collection system  Reduce GHG emission from climate friendly sewage sludge disposal |  | KFW implementing Water Resources Management Programme VI project during 2020 - 2026 . project activities:  Expansion of wastewater networks in South Amman  Expansion of Monolandfill next to As Samra WWTP with budget 48 M EUR ,the module pursues the overall developmental objective of making a contribution to the efficient and sustainable management of Jordan's scarce water resources to ensure a sustainable supply for the country. The measures will also contribute to a climate friendly wastewater disposal system in Jordan. Project preparation Increased capacity to collect and treat wastewater in the Jordan Valley Construction of wastewater networks in South Amman Expansion of Khirbat As-Samra WWTP (phase 3) 
|  |  | Construction of wastewater networks in South Amman | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 70 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) |  |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  | Construction of wastewater networks in Ma'an | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 10 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Construction of wastewater networks in Al-Karak |  | Coverage (%) of wastewater service | [7 empty] | KfW | EUR 29 M | Planned | Feasibility studies completed | Construction of wastewater networks in Al-Karak |  | KFW implementing Wastewater Karak project Construction of wastewater treatment plant Karak 29 M EUR The objective of the project is to ensure hygienic and environmentally sound sewage disposal and thus to contribute to improving hygiene in the project area and to protecting water resources. To ensure the sustainable operation of the Karak treatment plant a complementary measure is planned under which a service contract with a private operator is financed for at least two years.  Save freshwater resources through the provision of treated wastewater for irrigation systems Construction of wastewater networks in Al-Karak, currently in Commissioning phase
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 17.5 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Construction of wastewater networks in Dhulail, Hallabat, and Khaldiah |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 55 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Construction of wastewater networks in Al-jbarat, Al-Manarah, and other areas in Jarash |  | Coverage (%) of wastewater service | [9 empty] | Without support | Feasibility studies completed
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | MWI-WAJ | 12 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Expansion of Khirbat As-Samra WWTP (phase 3) |  | Coverage (%) of wastewater service |  |  |  |  | MWI-WAJ |  |  | KfW | EUR 48 M (part of same project as budget above) | Planned | Feasibility studies completed | Building of a Monolandfill (cell 1) next to As Samra WWTP through KfW project, Save freshwater resources through the provision of treated wastewater for irrigation systems  Improving the energy efficiency of the wastewater collection system  Reduce GHG emission from climate friendly sewage sludge disposal |  | KFW implementing Water Resources Management Programme VI project during 2020 - 2026 . project activities:  Expansion of wastewater networks in South Amman  Expansion of Monolandfill next to As Samra WWTP with budget 48 M EUR ,the module pursues the overall developmental objective of making a contribution to the efficient and sustainable management of Jordan's scarce water resources to ensure a sustainable supply for the country. The measures will also contribute to a climate friendly wastewater disposal system in Jordan. Project preparation Increased capacity to collect and treat wastewater in the Jordan Valley Construction of wastewater networks in South Amman Expansion of Khirbat As-Samra WWTP (phase 3
|  |  |  | new | Treated wastewater (%) reused |  |  |  |  | BOT | 230 million JOD
Full proposal available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Increased capacity to collect and treat wastewater in the Jordan Valley | new | Wastewater infrastructure and treatment plant serving the Jordan Valley designed and built |  |  |  |  | MWI-JVA |  |  |  |  | Without support | Concept note available
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Water harvesting (capture and storage) projects implemented in the Badia | ongoing | Number of water harvesting projects completed | 37 water harvesting projects completed from 2016 to present | 15 water harvesting projects | 15 water harvesting projects | 15 water harvesting projects | MWI-MOA | 6 million JOD |  |  |  | Without support | Concept note available
Amount of water captured and stored
Improvement in livelihood security by users
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Capacity of MOA staff to plan for climate change adaptation strengthened | new | Number of trained staff (60) |  | 30 staff trained | 15 staff trained | 15 staff trained | MOA |  |  |  |  | Without support | Concept note available
[5 empty] | Number of training workshops (12) |  | 4 workshops held | 4 workshops held | 4 workshops held |  | 130,000 JOD
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Grazing reserves by water harvesting sites established & rehabilitated | new | Area of new sites reserved for grazing established |  | Two new grazing sites (3000 donums) designed & established | Assessment studies completed | Vegetation cover in 2 degraded grazing sites (2000 donums) restored | MOA | 800,000 JOD |  |  |  | Without support | Proposal available
|  |  | Ecosystem services restored and sustainably managed |  | Area of degraded grazing reserves rehabilitated | [6 empty] | In-kind
|  |  | Livelihood activities diversified & poverty reduced in Badia |  | Increase in vegetation cover & livestock production |  |  | Training delivered to local community |  |  |  | Public land leased for free
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Agricultural Risk Management To reduce frost effects | new | no. of farmer participating in Training courses for plant and animal production farmers about how agricultural risk management to reduce their effects by use the new technology. |  |  |  |  | MOA. NARC | 9.00 MUS$ |  |  |  | Without support
|  |  | Reduce soil erosion through the management and harvesting of rainwater amongst small farmers in rural areas in Jordan | new | no of benificiers |  |  |  |  | MOA.,small Farmers |  |  |  |  | Without support
|  |  | Strengthening the capability of the private sector on marketing the agricultural products (Marketing services companies). | new | % of increaing in ex[ort of jordanian fruit and vegetables |  |  |  |  | MOA, private sector | 12 MUS$ |  |  |  | Without support | pre concept
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Rehabilitation of rangeland reserves implemented | new | Area of degraded rangeland rehabilitated |  | Assessments of soil & vegetation cover completed | 5,000 donums of rangeland planted w/ artiplex (saltbush) | Grazing activities regulated & training delivered | MOA | 500,000 JOD | In-kind |  |  | Without support | Proposal available
|  |  | Water harvesting systems designed & built |  | Number of water harvesting systems built | [6 empty] | Public land leased for free
Production increase in livestock
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Hima system for rangeland management implemented | new | Completion of soil & socioeconomic assessments | Replication of 1000 donums Hima project in Bani Hashem | Assessments completed and approved | Association set up | 5,000 donums under Hima restoration | MOA | 900,000 JOD | In-kind |  |  | Without support | Proposal available
|  |  | Community participation in rangeland management implemented |  | Adherence to Hima principles in rangeland use |  |  | Training delivered |  |  |  | Public land leased for free
|  |  | Ecosystem services restored and sustainably managed |  | Area of degraded rangeland rehabilitated |  |  | Buy-in secured | Grazing regulated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Water harvesting techniques introduced in rangeland |  | See water harvesting in Badia project in water sector (see details in Row 257) | [9 empty] | Without support
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Forestation of recreational parks |  | Number of parks established (5) |  | 2 parks established | 2 parks established | 1 park established | [5 empty] | Without support | Concept note available
|  |  | Mitigating soil erosion | new | Size of area forested (200 dunums) |  | 70 dunums forested | 70 dunums forested | 60 dunums forested | MOA | 3.5 million JOD | 350,000 JOD
|  |  | Creating jobs for low-income families tending ther parks |  | Number of trees forested (3,000) |  | 1,000 trees planted | 1,000 trees planted | 1,000 trees planted
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Water irrigation channels upgraded & maintained | ongoing | Length of water channels upgraded (30 Km) | 13.5 Km of water channels upgraded in 2018 | Completing the upgrading of 10 Km of water channels | Completing the upgrading of 10 Km of water channels | Completing the upgrading of 10 Km of water channels | MOA |  |  |  |  | Without support | Proposal available
|  |  | Springs and water sources protected from pollution |  | Agricultural water yield improved | [5 empty] | 1 million JOD | In-kind
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Income & resilience of poor families in rural areas and Badia improved by providing a package of free livestock and skills training | ongoing | Number of low-income families targeted (5,000) | 10,000 current beneficiaries | 1,500 families | 1,500 families | 2,000 families | MOA |  |  |  |  | Without support | Proposal & case studies available
[5 empty] | Improvement in income levels of beneficiaries | [5 empty] | 5 million JOD
Percentage of women beneficiaries
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | New jobs created through green works in agriculture and forestry | new | Number of new jobs created (1,000) |  | 250 jobs | 250 jobs | 500 jobs | MOA-Ministry of Labour-MOPIC-CBOs |  |  | FAO/EU | US 12 M | Ongoing | Concept note available | Enhancing resilient livelihoods and food security of host communities and Syrian refugees in Jordan and Lebanon through the promotion of sustainable agricultural development |  | Project implemented by FAO funded by EU with total budget 12 MUS$, forestry and rangeland rehabilitation activities will provide labour opportunities to 1,000 families for a period of 4 months and restore up to 1 110 ha of forest and rangelands. The project will cover the governorates of Irbid, Jarash, Balgaa, Madaba, Karak and Taffeila creating 149 700 man/day of work.
|  |  | Workers acquiring skills in forestation, terrace building, drip irrigation, cistern construction, and seedling production |  | Area of land newly forested (3,000 donums) |  | 1000 donum forested | 1000 donum forested | 2000 donum forested |  | 3 million JOD | 20% in-kind |  |  |  |  | Livelihoods and income generating opportunities for the most food insecure created through sustainable management of natural resources. |  |  | Develop models on use of organic waste at Zatari refugee camp to covert to composting, and use sludge from waste water treatment and organic waste to pilot a waste to energy project producing biogas and electricity in Zatari refugee camp
[5 empty] | Number of trees forested (270,000) |  |  |  | 270000 tree forested
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Assessment of the impact of climate change on water productivity of rainfed and irrigated crops in three regions (north, middle, and south) of Jordan | new | Prediction of changes in water productivity of crops in Jordan over 2020-2030 and 2040-2050 relative to base period 1985-2005 | Replication & expansion of an existing project | Collection of weather data and selection of crops | Agricultural survey completed | Report mapping water productivity changes published | MOA | 600,000 JOD |  |  |  | Without support | Concept note available
TBD
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Land reclamation implemented | new | Area of land reclaimed for agriculture (15,000 donums) | Replication of a concluded IFAD-financed project | Reclamation of 5,000 donums | Reclamation of 5,000 donums | Reclamation of 5,000 donums | MOA |  | MOA: 10% | IFAD | USD 15 M | Ongoing | Proposal available | IFAD implementing Rural Economic Growth and Employment Project I, during 2015- 2021 with total budget (15) MUS$ aimed to Improve access to finance in rural areas in Jordan. This is achieved through building technical and competitive capacities of small farmers as well as small- and medium-sized agricultural companies. In addition, the project works on integrating smallholder farmers into value chains, and creating employment opportunities in rural areas for women and youth. Thus, REGEP contributes to economic growth by increasing incomes, and increasing agricultural exports of fruit and vegetables |  |  | No. of new jobs created are 1300 by IFAD
[11 empty] | 8 million JOD | Farmers: 20% | [7 empty] | Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi, Technical assistance and financial incentives to farmers; ( $1,268,508 loans to SMEs + 204 people accessing rural finance (108 women) + 1 policy knowledge product).
[5 empty] | Amount of financial assitance offered to farmers | [14 empty] | No. of training workshops/No. of farmers trained are 1612 (583 women)
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Supplementary irrigation of rainfed olive trees implemented | new | Improvement in yield of rainfed olive trees |  | Awareness raising delivered | Supplementary irrigation applied to TBD donums | Yield improved by TBD% | MOA |  | MOA: 10% in-kind |  |  | Without support | Concept note available
|  |  | Yield of rainfed olive trees increased |  | Area of farmland served w/ supplementary irrigation | [6 empty] | Farmers: 5%
Cisterns built
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Organic agriculture methods introduced | new | Area of farmland converted to organic |  | Training delivered | Soil preparation on-going | Organic certification applications submitted | MOA-JSMO |  |  |  |  | Without support | Action Plan 2018-2022 available
|  |  | Contract farming introduced |  | Volume of contract farming concluded |  | Detoxification of farmland started |  |  |  | 4 million JOD over 4 years
Resiliency of small farmers and rural women strengthened
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | School children trained to plant, care for, and harvest olive trees in their schools using treated greywater |  | Number of olive trees planted (9,000) | Since 2017, 2950 olive trees have been planted in 37 schools | 3,000 olive trees planted in 35 schools | 3,000 olive trees planted in 35 schools | 3,000 olive trees planted in 30 schools | MOA |  | 5,000 olive trees donated by philanthropist |  |  | Without support | Concept note available
|  |  |  | ongoing | Number of participating schools (100) |  |  |  |  | Philanthropists | 100,000 JOD
Mainstreaming use of treated greywater for irrigation
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Domestic/small scale aquaponics production units installed | new | Number of units installed (300) |  |  |  |  | MOA |  |  |  |  | Without support
[5 empty] | Small scale aqauaponics production demonstrated | Designs completed | 100 units installed | 100 units installed | 100 units installed |  | 1 million JOD
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Economic empowerment of rural women |  | Permanent farmer markets set up (3) in three cities |  | 1 market set up in Amman | 2 markets set up in Irbid & Zarqa | Overall, 75,000 beneficieries | MOA-Ministry of Industry and Trade-Ministry of Health-Ministry of Social Development-JSMO-CBOs | 10 million JOD |  | Netherlands |  | Ongoing | Concept note available | Contribute to the increased competitiveness and performance of Jordanian horticulture produce in a variety of export markets, rural job creation and income generation in horticulture. Establishing a web-portal providing the agriculture sector in Jordan with market intelligence. Build producer Association capacity to deliver services to the sector and to develop a market ambition for the industry. |  | Pilot Project Inclusive Horticulture Value Chains Jordan is a pilot project, which has started at the beginning of 2019, to assist the small and medium sized farmers that are not (yet) able to access advanced greenhouse technology. The pilot project is implemented by a consortium led by Advance Consulting in collaboration with WUR, Profyta, and Holland Door. This pilot project aims to contribute to the increased competitiveness and performance of Jordanian horticulture produce in a variety of export markets, rural job creation and income generation in horticulture. Taking into account the delicate balance between delivering short-term results and establishing strategies that will be sustainable in the long run, the consortium aims for a practical, knowledge-based and market-oriented approach to improving farmer and sector performance. This pilot aims at feasible low cost interventions that have a significant impact. Farmers are being connected to work on export oriented production with the involvement of exporters, some of whom are also part of a CBI training program. The farmers receive capacity building and support for the whole production chain (seed selection, irrigation management, IPM (Integrated Pest Management), bush management, greenhouse design, etc.), enabling them to enhance earning capacity while reducing water and energy use. The pilot project identifies best practices which can be replicated and scaled up elsewhere in Jordan.
|  |  | Enhancing skills of rural women in food production & marketing | new | No. of food production & marketing workshops |  | 5 workshops | 5 workshops | 5 workshops |  |  |  | ILO | [5 empty] | Export Promotion is a project by the Centre for the Promotion of Imports from developing countries (CBI) which focuses on export coaching for Jordanian exporters. Jordan aims to make the transition from a supply driven towards a demand driven Fresh Fruit and Vegetables (FFV) sector. Demand should be driving export, not supply. This transition will require a better understanding of market demand, market systems, market requirements and also a change in production and the supply chain of companies and the sector at large. CBI supports the Jordanian Ministry of Agriculture in establishing a web-portal providing the agriculture sector in Jordan with market intelligence. With regard to export coaching, CBI builds the capacity of a selected pool of exporters. CBI collaborates with Jordan Exporters and Producers Association for Fruit and Vegetables (JEPA) to build their capacity to deliver services to the sector and to develop a market ambition for the industry. Moreover, CBI is setting up a sector platform for private-public dialogue with the Jordanian Ministry of Agriculture, JEPA, associations, farmers and exporters. To stimulate market led agriculture, CBI works closely together with Eco Consult and Advance Consulting in order to provide farmers with the right information regarding crop selection. The collaboration with ILO concerns compliance with international labour standards that are increasingly a condition for export.
|  |  | Enhancing livelihood of rural women and their families |  | No. of new jobs created for rural women (900) |  | 300 jobs created | 300 jobs created | 300 jobs created
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Home gardens promoted | new | Number of agricultural associations engaged |  | 35 agricultural associations engaged | 35 agricultural associations engaged | 35 agricultural associations engaged | MOA |  |  |  |  | Without support
|  |  | Household food security achieved | [7 empty] | 500,000 JOD over 4 years | In-kind
Agricultural associations activated
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Improving productivity of farmers thru mechanized farming |  | No. of mechanized equipment introduced (50) |  | 15 machines | 20 machines | 15 machines | MOA |  |  |  |  | Without support | Concept note available
|  |  | Area of cultivation expanded - Reduction in harvest loss | new | No. of workshops for field stations (120) |  | 50 workshops | 90 workshops | 20 workshops | Jordanian Agricultural Engineering Association | 7 million JOD
|  |  | New jobs created |  | No. of new jobs created (1,150) |  | 345 new jobs | 460 new jobs | 345 new jobs
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Capacity of recent university graduates and the unemployed enhanced thru training and establishment of hydroponics and aquaponics incubators | new | Number of trainees (1,080) |  | 360 trainees | 360 trainees | 360 trainees | MOA | 6.3 million JOD |  | Netherlands | EUR 0.89 M | Planned | Concept note available |  | Netherlands support strengthening the skills development for WWT and agricultural reuse | Netherland embassy in Jordan Funded by OKP 2020- 2021 0.890 M EUR; Activities: Recently established diploma programme at the Al-Balqa’ Applied University Enhancing the competitiveness of Jordanian produce on national, regional, and international markets through adoption of improved technologies for sustainable and efficient agriculture and introducing market-driven approaches to improve productivity and reduce water use; Strengthening horticultural business partnerships and creating market systems;  expanding the pool and skills of human resources in hydroponics and postharvest management to prepare for labour market entry;  Creating employment opportunities in commercial farming and agribusinesses, especially for vulnerable communities;  Improving livelihood opportunities through implementation of hydroponic packages and improved postharvest at the community level with households and community based organizations (CBO). An important target group was the large scale farmers who can afford investments in advanced greenhouse technology and who can – after positive outcomes – stimulate a trickling down effect to medium and eventually small scale farmers.
[5 empty] | Number of workshops (54)/Number of ToTs (6) |  | 18 workshops/2 ToTs | 18 workshops/2 ToTs | 18 workshops/2 ToTs | CBOs | [7 empty] | Hydroponic Agriculture and Employment Development
[5 empty] | Number of incubators (6) |  | 2 incubators | 2 incubators | 2 incubators |  |  |  | FAO
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Re-settlement of date palm trees in Al-Azraq ecosystem | new | Area of land planted with datepalm trees |  | Needs assessment completed | Water irrigation system powered by solar PV installed | Water harvesting structures rehabilitated | MOA |  |  |  |  | Without support | Proposal available
|  |  | Income-generating activities for rural communities supported |  | Energy saving from PV-powered pumping system | [5 empty] | 5 million JOD over 4 years
|  |  | Green cover deterioration and desertification risk mitigated |  | Number of jobs created by project |  | 100 donums planted
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Increasing the resilience of displaced persons to climate change-related water challenges in urban host settlements | new | KPIs cannot be defined because the project to enhance resiliece has not been selected yet |  |  |  |  | MWI-MoEnv-MOPIC-MOMA-Municipalities of Irbid and Mafraq |  |  | UN Habitat-Global Adaptation Fund |  | Planned | AF approved Concept note | National components including the following interventions: Rainwater harvesting from roof tops in mosques, schools, municipal buildings and households; Grey water systems treatment and reuse in schools; The application of sustainable agriculture practices through permaculture at the JUST Faculty of Agriculture’s premises The project will focus on responding to climate change-related water challenges by taking a sustainable water management approach. | The proposal developed and currently under financial process evaluation, expect to start of implementation in 2nd half 2020 | at final stage of financial process in Adaptation Fund | The Adaptation Fund has approved financing their proposal titled “Increasing the Resilience of both Displaced Persons and Host Communities to Climate Change-Related Water Challenges in Jordan and Lebanon” with grant 14MUS$.
[7 empty] | TBD by August 2019 | TBD by August 2019 | TBD by August 2019 |  | $7 million for National Component |  |  |  |  | Full proposal submitted to AF
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Enhancing community resilience by building a 100 Km green belt and launching ecosystem-based enterprises inside forested areas located east of Amman and Zarqa at the desert edge | new | Decrease in desertification |  | Action plan prepared | Site prepared | Trees planted | CBOs/NGOs-MoEnv-JEF-MOA-MWI-MOMA-MOPWH-RSCN-CSBE |  |  |  |  | Without support | Concept note available
[5 empty] | Planting appropriate tree species |  | Tree species selected | Eco-system based investments approved | Eco-system based projects implemented |  | 2.5 million JOD
[5 empty] | Investment plans in ecosystem-based projects prepared |  | Design completed
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Sustainable recreational parks developed and managed by community-based organizations (CBOs) in each Governorate | ongoing | Number of sites identified and developed (12) | 3 sites identified | 3 parks implemented | 3 parks implemented | 3 parks implemented | MoEnv-JEF-MOA-MOMA-MoTA-CBOs & NGOs-Private sector actors | [5 empty] | Concept note available
[6 empty] | Concept developed | 3 additional parks identified | 3 additional parks identified | 3 additional parks identified |  | $2.3 million |  | UNDP-AfD
[5 empty] | CBOs identified and selected | Funding identified
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Enhancing the capacity to store water and provide cash by building 500 water cisterns | ongoing | Number of water cisterns built (500) | 500 cisterns built | Effect of cisterns on socio-economic conditions assessed |  |  | MOA |  |  |  |  | concluded |  | The International Labor Organization (ILO) is exploring specific areas where the ILO has technical expertise, tools, and intervention models that could be of contribution. Potential support provided in the following areas: 500 water cisterns built with a labor intensive approach to improve water collection and increase agriculture.
[5 empty] | Number of worker beneficiaries | [7 empty] | ILO-FAO
Impact of water storage on target communities
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Conservation of local landraces | new | Mainstreaming the use of landraces |  |  |  |  | NARC |  |  |  |  | Without support | Full proposal available
|  |  | Strengthening resilience of ecosystems to climate change stresses |  | Breeding toward resilience, value, and quality |  |  |  |  | MOA | 500,000 JOD
|  |  | Enhanced adaptive capacity & income for small farmers |  | Upgrading of the gene bank
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Prioritized adaptation practices implemented | new | Improvement in crop yield |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Efficient planning & use of resources & enhancing productivity |  | Implementation of soil & water adaptation practices |  |  |  |  | MOA | 250,000 JOD
|  |  | Increased farm income & investment in CC adaptation |  | Poverty alleviation |  |  |  |  | MWI-MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Identification of suitable water harvesting sites in Badia | new | GIS mapping of water harvesting sites |  |  |  |  | NARC | [5 empty] | Concept note available
|  |  | Scenarios developed for applying water harvesting techniques |  | Water harvesting scenarios developed |  |  |  |  | MOA | 120,000 JOD |  | ICARDA-FAO
|  |  | Rehabilitated vegetation cover and pastures |  | Awareness-raising for local communities |  |  |  |  | MWI
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Conceptual framework combining silvicultural, ecological and community-based approaches for afforestation & honeybee foraging | new | Afforested dryland area & plant selection |  |  |  |  | NARC |  |  |  |  | Without support | Full proposal available
[5 empty] | Integration of local communities |  |  |  |  | MOA | $970,000
|  |  | Developing new knowledge-based policy for afforestation |  | Extended area of honeybee foraging
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Selecting new varieties of wheat with increased salinity tolerance | new | No. of salinity-resistant wheat varieties selected |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Wheat cultivation expanded to new areas |  | Area expanded for wheat cultivation |  |  |  |  | MOA | 200,000 JOD
MWI
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Sustainable, participatory roadside afforestation implemented | new | Number of trees planted |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Reduced poverty by providing afforestation jobs |  | Number of extension workshops conducted |  |  |  |  | MOA | 600,000 JOD
|  |  | Improved ecosystems and enhanced biodiversity |  | Number of people trained on afforestation |  |  |  |  | MWI-MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Building gardens in public schools using permaculture | new | Number of participant schools/trained students |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Introducing permaculture in vocational education courses |  | No. of permaculture training courses developed |  |  |  |  | MOA | 250,000 JOD
|  |  | Students awareness of land, wild outdoors, and health raised |  | Quality of school permaculture gardens |  |  |  |  | MoEdu
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Risks of climate change on epidemiology of plant pests assessed | new | No. of awareness raising events conducted |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Farmers and extension agents awareness of new pests and control measures developed |  | Communication tools to educate farmers |  |  |  |  | MOA | 120,000 JOD
[5 empty] | Warning system about risks designed |  |  |  |  | MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Scaling up cultivation of quinoa as an adaptation action | new | Developing technical packages for quinoa |  |  |  |  | NARC |  |  |  |  | Without support | Full proposal available
|  |  | Improved food and nutritional security in poor communities |  | No. of training workshops/No. of farmers trained |  |  |  |  | MOA | $850,000
[5 empty] | Area targeted for quinoa cultivation |  |  |  |  | MWI
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Crop modeling framework to improve management of cropping systems and provide farmers with CC adaptive measures | new | Productivity incease in rain-fed crops |  |  |  |  | NARC |  |  | IFAD | USD 23.991 M | Ongoing | Full proposal available | IFAD implementing Small Ruminants Investment and Graduating Households in Transition project during 2017- 2023 with total budget 23.991 MUS$ IFAD Activities have focused mainly on rain-fed agriculture and livestock, small farm credit, income diversification and natural resources management. Extension and animal health services, water scarcity, feed shortages and degraded rangelands. Project implemented in the northern and central.
[5 empty] | Efficiency of natural resource use (water, soil) |  |  |  |  | MOA | 500,000 JOD
|  |  | Exploration of crop scenarios facilitated using expert system |  | Dissemination of results thru farmers training |  |  |  |  | MWI-MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Dissemination of conservation agriculture to increase wheat and barley production in dry areas using improved varieties | new | No. of trainings on CA practices delivered |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
[5 empty] | Identifying wheat landrace adapted to no-till |  |  |  |  | MOA | $600,000
|  |  | Enhancing food security under climate change scenarios |  | Improvement in soil productivity |  |  |  |  | MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Development of high efficiency gray water treatment system using coagulation and flocculation materials extracted from plants | new | [5 empty] | NARC |  |  |  |  | Without support | Concept note available
[5 empty] | Amount of treated gray water re-used in irrigation |  |  |  |  | MOA | 500,000 JOD
MWI
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Development of gray water treatment system using shredded tire as bio-filter | new | Effectiveness of shredded tire filtration system |  |  |  |  | NARC |  |  |  |  | Without support | Full proposal available
[5 empty] | Results of soil, crop, and water monitoring |  |  |  |  | MOA | $400,000
No. of training sessions delivered to beneficiaries
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Treatment of gray water and re-use demonstrated | new | 20 graywater treatment units will be installed in each of six villages |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Scale-up of gray water treatment and reuse in home garden irrigation using findings from NARC development studies/projects | [6 empty] | MOA | 500,000 JOD
[5 empty] | No. of public awareness & education workshops |  |  |  |  | MWI
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Land use change mapped in Amman (1984 to 2018) using GIS and remote sensing methods to detect changes in vegetation cover | new | Spectral vegetation indices on satellite images |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
[5 empty] | Sharing of research results with decision-makers |  |  |  |  | MOA | 100,000 JOD
|  |  | Awareness of impact of urbanization on agricultural land raised |  | Changes in land use laws and policies |  |  |  |  | GAM-MoEnv
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Improving rural livelihood by developing Carob cultivars | new | National survey of Carob tree species |  |  |  |  | NARC |  |  |  |  | Without support | Full proposal available
|  |  | Diversified farm income and enhanced resiliency |  | Propagating Carob species in protected areas |  |  |  |  | MOA | 250,000 JOD
Raised awareness about Carob species
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Improved field pest control using sustainable pest management | new | Rearing and adding natural enemies to soil |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
|  |  | Enhanced adaptive capacity and resiliency of plants |  | Number of awareness campaigns and workshops |  |  |  |  | MOA | 250,000 JOD
Plant resistance and tolerance to soil pathogens
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Method to detoxify olive oil mill wastewater demonstrated |  | Purification method tested using nano-materials |  | Fabrication of nano-material completed | Testing of nano-material completed | Technology demonstrated | NARC |  |  |  |  | Without support
|  |  | Environmental chemistry lab established for pollutant detection | new | Environmental chemistry lab established |  |  |  |  | MOA | 500,000 JOD |  |  |  |  | Full proposal available
Protecting ecosystems and water resources from OMW pollution
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Integrating climate change adaptation and mitigation into the watershed management plan of Wadi Shouib | new | Development of watershed management plan |  |  |  |  | NARC |  |  |  |  | Without support | Concept note available
[5 empty] | Number of green jobs created in the wadi |  |  |  |  | MOA | 450,000 JOD
|  |  | Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi |  | Technical assistance and financial incentives to farmers
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Sustainable land use planning to improve land productivity and increase ecosystem integrity | new | Guidance tools for agricultural land use developed |  |  |  |  | NARC | 150,000 JOD |  | UNDP support by WASH | 0.5 MUS$ | Ongoing | Concept note available | UNDP is currently implementing a project that aims to strengthen the national drought governance system in Jordan and promote a more systematic approach to drought response planning and management including the establishment of an early warning system and designing and implementing awareness programs on drought hazards and impacts. |  |  | Agreement signed with the Inter-Islamic Network for Water Resources Development and Management (INWRDAM) and implementation has been initiated
MOA
|  |  | Appropriate adaptation interventions identified to restore degraded lands and rangelands and improve resiliency to drought |  | Land use scenarios proposed under climate change conditions, pointing out potential productive lands to increase income generating opportunities and food supply |  |  |  |  | MoEnv
|  | Raising/combining climate finance | A revolving loan fund for supporting climate change mitigation and adaptation action by farmers created |  | Size of fund raised (10 million JOD) |  | 3 million JOD raised | 3 million JOD raised | 4 million JOD raised | Agricultural Credit Corporation |  |  |  |  | Without support
|  |  |  | new | Number of beneficieries (4,500) |  | 1,500 beneficieries | 1,500 beneficieries | 1,500 beneficieries |  | 10 million JOD | 5%
MOA
|  | Raising/combining climate finance | Strengthening institutional capacity of Jordan Environmental Fund (JEF) to enhance ability of JEF beneficiaries (NGOs & public sector actors) to implement CC mitigation and adaptation actions | ongoing | No. of stakeholders engaged annually | JEF strategy updated | Operations manual and gender policy plan approved | M&E plan approved | Funding accreditation achieved | [5 empty] | Without support
[5 empty] | Technical assistance unit established at JEF | Institutional building of JEF is on-going |  | Technical unit set up |  | MoENV-JEF
[5 empty] | Amount of funding raised |  |  | Raising $25 million
| Monitoring and Evaluation (M&E) | Data collection and management | M&E and data analysis for water (focus on water for agricultural use) and waste (focus on solid waste) sectors | new | Plan of action for measurement and verification prepared |  |  |  |  | MWI, MOA, MoE |  |  | UNEP/IKI | EUR 0.492 | Planned |  |  | Support and accelerate public and private investment in sector specific NDC implementation | UNEP preparing for implementing project funded by IKI with total budget 0.492 M EUR during 2020-2023,Based on scoping mission on Feb.2020, Agreement with Ministry of Environment on selection of two sectors for prioritization: • Waste, with focus on solid waste • Water, with focus on water for agricultural use Work is ongoing to elaborate actions and specific outputs under these sectors. | No progress
Improvement on NDC target in water sector
Improvement on NDC target in waste sector
| Capacity Building & Lesson-Learning | Feasibility studies (social, technical, economic) | Feasibility study of rehabilitating irrigation distribution network in the Northern section of the Al-Aghwar conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | 260000
|  | Feasibility studies (social, technical, economic) | Feasibility study of rehabilitating irrigation distribution network in the mid section of Al-Aghwar conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | 220000
|  | Feasibility studies (social, technical, economic) | Feasibility study of rehabilitating irrigation distribution network in the Northeastern section of Al-Aghwar conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | 290000
|  | Feasibility studies (social, technical, economic) | Feasibility study of introducing SCADA system in Southern region of Jordan Valley conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | 700000
|  | Feasibility studies (social, technical, economic) | Wadi Nkhail dam project feasibility study conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | $2 million
|  | Feasibility studies (social, technical, economic) | Technical study of the Tilal Dhahab dam project conducted | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | $2 million
|  | Feasibility studies (social, technical, economic) | Feasibility Study to reduce water losses and increase water savings in the northern part of King Abdullah Canal | new | Feasibility study prepared & approved |  | Feasibility study prepared & approved |  |  | MWI-JVA | 0.5 MUS$ |  |  |  | Without support
|  | Feasibility studies (social, technical, economic) | Feasibility study on the transfer of treated wastewater from the South Amman wastewater Treatment plant to the Wadi Husban dam and conveyance to the King Abdullah Canal | new |  |  | Feasibility study prepared and approved |  |  | MWI-JVA |  |  |  |  | Without support | Water Sector Capital Investment Program 2016-2025
[5 empty] | Feasibility study prepared & approved | [5 empty] | $2.2 million
iii. OBJECTIVE: Adaptation to climate change strengthened in multiple sectors (ecosystems, gender-based resiliency, health, local governance, social conditions, etc.) |  |  | ii. OUTPUTS |  | iii. Key Performance Indicators (KPIs) | iv. Baseline | v. Targets |  |  | vi. Lead ministry | vii. Funding requirements | viii. Cost co-share | ix. Implementing Partner(s) | x. Budget | xi. Status | xii. Relevant concept notes and proposals or strategies
|  |  | Output statement | Status |  |  | Yr 1 2019 | Yr 2 2020 | Yr 3 2021
| Policy, Strategy & Legislation | Policy analysis/support (cost-benefit analysis | An assessment of the relative benefits of the 35 individual NDC actions for reducing GHG emissions (i.e. mitigation) and reducing potential climate impacts (i.e. adaptation) versus their cost. | new | Cost-benefit analysis – as an assessment of the relative benefits of the 35 individual NDC actions | NDC AP |  |  |  | MoEnv. | 100,000 US$ |  | Ricardo |  | Planned | NDC AP | Through CAEP, Ricardo will implement Cost-benefit analysis – as an assessment of the relative benefits of the 35 individual NDC actions for reducing GHG emissions (i.e. mitigation) and reducing potential climate impacts (i.e. adaptation) versus their cost.
|  | Policy analysis/support (cost-benefit analysis; vulnerability assessments) | Improved conservation status of climate vulnerable ecosystems and strengthened adaptive capacities of key ecological hotspots | new | Vulnerability assessment of ecosystems to climate change updated | Third National Communication (TNC) report | Vulnerability assessment approved by RSCN |  |  | MoEnv-ASEZA-PTDRA | 200,000 JOD | 5% (in-kind contribution: staff time, etc) |  |  | Without support | Proposal for funding will be submitted in 2019 to GCF
GCF (pending)
|  | Policy analysis/support (cost-benefit analysis; vulnerability assessments) | Conservation plan for climate vulnerable ecosystems updated and network of protected areas (PAs), revised PA buffer zones, and spacial conservation areas (SCAs) officially established | new | PA network update report published | 2008 PA Network Conservation Plan & sensitivity map | Desktop assessment conducted & field assessment designed | Field assessment conducted & PA network report developed | PA network report finalized & PA network approved by MoEnv | RSNC |  | 10% (in-kind contribution: staff time, etc) | CEPF/ IPA |  | Concluded | Draft concept note available | project has ended
[5 empty] | Proposed PAs, revised PA buffer zones, and SCAs officially established |  |  |  |  | MoEnv-ASEZA-PTDRA |  |  | GEF/ UNDP |  |  | Proposal for funding will be submitted in 2019 to GCF
GCF (pending)
|  | NDC mainstreaming at the national and subnational level | Enhanced capacities to develop mitigation and adaptation plans | ongoing | Enhanced ability to formulate and implement CC actions (mitigation and adaptation) and sustainable energy policies at local levels |  |  |  |  | MoEnv. MOPIC |  |  | UNDP | 1 MUS$ | Ongoing | Proposal available | UNDP implementing project funded by GEF :  The National circumstances chapter of the 2nd BUR and 4th National Communication was prepared and will be validated with all concerned stakeholders during the 2nd quarter of 2020.  Training on the IPCC 2006 guidelines for the national technical staff involved in the inventory of anthropogenic emissions.  The national inventory of anthropogenic emissions by sources and removal by sinks of all greenhouse gases (GHGs) not controlled by the Montreal Protocol, including a national inventory report was initiated and in its final stage.  Jordan initiated the climate change impact assessment on the water, agriculture and biodiversity sectors. |  |  | The second Biennial Update Report has been finalized and under revision, expected submission date end of Nov. 2020
[10 empty] | MOMA |  |  | EU/ClimaMed |  | Planned |  | A draft for action plan has been developed for each city covering the sectors included in the SEACAP formulation. |  | Clima-Med Acting for Climate in South Mediterranean focuses on supporting sustainable energy policies and strategies both at national and local levels; Providing technical assistance to support the formulation and implementation of local Sustainable Energy Access and Climate Action Plan (SEACAPs),The Clima-Med experts have conducted of January 2020, a number of field visits in Jordan that took place in the municipalities’ premises. . One of the main objectives of these visits was to support the local authorities in identifying the city priority projects related to the mitigation and adaptation of climate change in all sectors by providing technical assistance to understand and respond more actively to climate change and to formulate and implement more sustainable projects such as renewable energy solutions, energy efficiency measures to reduce CO2 emissions, solid waste management, efficient water usage, water harvesting and environmental – friendly transport.Structured to lead brainstorming sequences with the cities allocated staff involved in the SEACAP development, the sessions aimed at identifying the cities’ sustainable development projects, the problems and challenges they face and the priority action plan in order to be able to speed up its development, financing and implementation. Based on the deep analysis done for all sectors in each of the cities, the experts succeeded in identifying and prioritizing the actions and measures to be taken to mitigate and adapt to climate change. Therefore, a draft for action plan has been developed for each city covering the sectors included in the SEACAP formulation. Consequently, the cities have shown interest and willingness to speed up the development of the identified actions and commit themselves to deliver their work. As where the National Authorities are supporting the cities in their sustainable development projects and are providing them with the necessary technical assistance as well as the financial means when it is available. | Technical assistance task for the Southern Neighborhood region, including Jordan, to enhance municipalities to develop sustainable energy and climate action plans, to support climate action
|  |  | Increased number of local sustainable actions (SEACAPs) | [6 empty] | Municipalities | TBD | TBD | GIZ |  | Ongoing | Proposal available |  | Under project "Supporting effective governance for NDC review and implementation in Jordan (IKI NDCs)" GIZ in cooperation with ministry of Environment Developing a framework for enhanced transparency in Jordan that includes contributions to Monitoring, Review and Verification (MRV) and M & E for Adaptation and Localization of NDC through developing three local climate action plans (LCAPs) and supporting the implementation of one pilot measure | under implementation | 1. Development of a detailed methodology for NDC revision to be approved and verified by stakeholders 2. Training for national partners in data management for GHG Emissions inventory and calculations 3. Developing three local climate action plans (LCAPs) for the first time in Jordan and supporting the implementation of one pilot measure.
[13 empty] | W.B |  | Ongoing |  |  |  |  | Amman Climate Plan Financing strategy
[15 empty] | Concluded |  |  |  |  | Design of the digital finance platform with Development of business case for digital finance platform with JOPACC and Development of Green Bonds guidelines
|  |  | assessment of the potential sources of financing for the prioritised options | [6 empty] | MoEnv. |  |  | Ricardo |  | Planned |  | Through CAEP, Ricardo plans to develop of a strategy for climate finance – we interpret this as an assessment of the potential sources of financing for the prioritised options, including both public and private sources, and domestic and international sources. |  |  | • Ricardo has received most data needed and will now begin to analyze and form initial reviews. • The main issue to be raised is that Ricardo has reached out to partners to cross-check cost and benefit information to make sure it is in line. o More inputs on benefit quantification would be helpful, either from experience of Jordan or in the region
|  |  | Improved access to financing mechanisms | [6 empty] | MoEnv.
|  | NDC mainstreaming at the national and subnational level | Enhanced capacities in Aqaba Special Economic Zone Authority (ASEZA) to develop mitigation and adaptation plans | new | Legislative and policy mechanisms to mainstream climate change action in ASEZA developed & approved | Legal review of environmental laws in ASEZA | Legal framework developed | Legal framework approved | Integrating carbon sinks into mitigation & adaptation policies | JREDS | 50,000 JOD | 5% |  |  | Without support | Concept note can be provided on a short notice
ASEZA
| Budgeting and Investment | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Health sector preparedness strengthened | new | Database for climate sensitive disease established |  | 20% of surveillance centers established | More surveillance centers established at rate of 20% per year | Incidence & forecast of climate sensitive diseases determined | Ministry of Health | 1.7 million JOD |  |  |  | Without support | "National climate change health adaptation strategy and action plan" available
|  |  | Surveillance system for climate change sensitive diseases established in 15 sentinel hospitals and 20 health centers |  | Incidence and prevalence of climate sensitive diseases determined | [6 empty] | 0
[7 empty] | Database developed |  |  |  | over 5 years
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Surveillance system for occupational climate change sensitive diseases established | new | Database for occupational climate sensitive disease established & incidence and prevalence of occupational climate sensitive diseases determined |  | 30% of centers set up | 30% of centers set up | 40% of centers | Ministry of Health | 1.56 million JOD |  |  |  | Without support | "National climate change health adaptation strategy and action plan" available
[7 empty] | Health units set up | Health units set up | Health units set up |  |  | 0
[7 empty] | Training conducted | Training conducted | Training conducted |  | over 3 yrs out of 7 yrs
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Leishmania Unit in Division of Parasitic and Zoonotic Diseases established | new | Preparedness of public health system to diagnose, monitor, and treat leishmania strengthened |  | Entomology section & leishmania strain unit established | Medical doctor hired | Monitoring & treatment of leishmania launched | Ministry of Health | 300,000 JOD |  |  |  | Without support | "National climate change health adaptation strategy and action plan" available
[8 empty] | Training conducted |  |  |  | 0
Awareness raised
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Enhancing income of rural families falling below the poverty line | new | Number of new income-enhancing projects introduced (18) |  | 6 new projects introduced | 6 new projects introduced | 6 new projects introduced | Ministry of Social Development (MoSD) |  |  |  |  | Without support
|  |  | New jobs created | [7 empty] | 540,000 JOD
|  |  | Improved development services in local community |  | Number of participating CBOs (18) |  | 6 participating CBOs | 6 participating CBOs | 6 participating CBOs
|  | MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources) | Income and agricultural productivity projects targeting poor rural households expanded |  | Number of additional projects introduced (15) | 18 projects delivered between 2010-2018 | 5 additional projects introduced | 5 additional projects introduced | 5 additional projects introduced | Ministry of Social Development (MoSD) |  |  |  |  | Without support
|  |  |  | ongoing | [6 empty] | 300,000 JOD |  |  |  |  | Feasibility study available
|  |  | Income diversification for rural households |  | Number of new jobs created (90) |  | 30 new jobs created | 30 new jobs created | 30 new jobs created
| Capacity Building & Lesson-Learning | Training needs in any of the other areas/sections | Enhancing capacity of MoSD staff to design and deliver climate resilient services to women and the poor | new | Number of training workshops (9) |  | 3 workshops held | 3 workshops held | 3 workshops held | Ministry of Social Development (MoSD) |  |  |  |  | Without support
[5 empty] | Number of trainee beneficiries (225) |  | 75 MoSD staff trained | 75 MoSD staff trained | 75 MoSD staff trained |  | 85,000 JOD | In-kind
|  |  | Raising awareness of MoSD staff of climate change risks & actions |  | Improvement in qualities of MoSD programs
|  | Training needs in any of the other areas/sections | Enhancing leadershjp capacity of community-based groups (CBOs) to address climate change | new | Number of training workshops (15) |  | 5 workshops held | 5 workshops held | 5 workshops held | Ministry of Social Development (MoSD) |  |  |  |  | Without support
[5 empty] | Number of CBOs eficiries (20) |  | 7 participating CBOs | 7 participating CBOs | 6 participating CBOs |  | 150,000 JOD | In-kind
|  |  | Raising women's awareness of climate change risks & actions |  | Improvement in poverty reduction programs
|  | Training needs in any of the other areas/sections | Contribution of non-governmental actors in ASEZA to support NDC implementation increased | new | Capacity of sectors/institutions within Aqaba to act on climate change strengthened | Integrated Coastal Zone Management (ICZM) action plan | Capacity building workshops on CC conducted | Capacity to calculate GHG emissions strengthened | Capacity to calculate mitigation outcomes strengthened | The Royal Marine Conservation Society of Jordan (JREDS) | 100,000 JOD | 5% |  |  | Without support | Concept note can be provided on a short notice
|  | Feasibility studies (social, technical, economic) | Capacities of non-governmental actors in ASEZA to conduct climate change research enhanced | new | Assessment of blue carbon storage and emission in Gulf of Aqaba published by non-governmental actors | Elementary maps of corals, seagrass beds, and sandy areas | Marine habitat maps for Gulf of Aqaba prepared | Carbon sequestration by ecosystems in Gulf of Aqaba determined | Carbon loss by marine ecosystems monitored over 5 yrs | JREDS | 500,000 JOD | 3% |  |  | Without support | Concept note can be provided on a short notice
ASEZA
over 5 years
|  |  | Blue Economy Principles for Improved Touristic Competitiveness, Livelihoods of the Fishermen Community, Industrial Development and Monitoring Indicators of Pollution Control and Climate Change in the Jordanian Sector of the Gulf of Aqaba, Red Sea | new | Environmental Quality Standards |  |  |  |  | ASEZA |  |  |  |  | Without support

## Facilitator Progress Tracking
Objective | Output | Progress on Implementation |  | Progress on Financing
|  | Q3 2020 | Q4 2020 | Q3 2020 | Q4 2020
1. Transition to a low carbon economy (increased share of renewable energy in total energy mix; upscaling energy efficiency measures in multiple sectors; mitigation of methane emissions) | Improved energy efficiency legal & institutional framework
Rooftop solar PV systems installed in residential buildings
Solar water heaters installed in residential buildings
Rooftop solar PV systems installed in public school buildings
Rooftop solar PV systems installed in houses of worship
Energy audits conducted in public buildings
Residential buildings retrofitted with roof and wall thermal insulation
Energy audits and energy efficiency measures implemented at industrial small and medium enterprises (SMEs)
Enabling small-scale farmers vulnerable group in the agricultural sector of the use of renewable energy categories. To improve their livelihoods and food security
Old refrigerators replaced with more efficient, energy-labelled refrigerators
LED lamp fixtures replacing incandescent and fluorescent lamp fixtures in residential buildings
RE systems installed for small-scale poultry and cattle farmers
Renewable energy adopted for water pumping, as follows:
Khirbat As-Samra WWTP (100% renewable)
Small to medium-sized WWTPs (100% renewable)
From sun rays to water drops
Energy over water reservoirs
In-pipe hydro in Aqaba
In-pipe hydro in Sweimeh
Floating PV
Powering the Wadi Al-Arab transmission line
Al-Aqeb well field PV plant
Disi Expansion
Azraq solar pumping
Al-Lajjun solar pumping
Energy efficiency measures implemented in the water sector:
Zai-Dabouq water transmission system + RE
Rehabilitation of pumping stations and well fields
Optimization of 26 pressurized transmission lines
Improvement of water supply systems in Madaba and Irbid
Hydro pumped storage
Construction of a 100 MWp PV solar power plant (wheeling scheme) to provide power to SMEs
Construction of concentrated solar power (CSP) units at SMEs for industrial thermal heating purposes
Natural gas supply infrastructure installed at SMEs
Phasing out use of diesel and liquid fuels at SMEs
Access to public transport services increased in Jarash
Access to public transport services increased in Irbid and Zarqa centers
Fostering mobility in Amman through a Bus Rapid Transit (BRT) network
Fostering mobility between Amman and Zarqa through a Bus Rapid Transit (BRT) line
Battery-electric passenger vehicles deployed for use in public/government fleets
Implement and applied ITS in puplic transportation
Solar Powered Electric Bus Fleet Pilot in Karak, Ma’an and Tafeilah Governorates
Battery-electric buses deployed for use in public transport
Battery-electric bikes deployed for use by university students
Demonstration-scale geothermal energy plant for heating and cooling designed and constructed
Energy efficient LED street lighting installed in municipalities
Rooftop solar PV systems installed in municipal buildings
Green building design principles and practices demonstrated
Construction of 3 green model homes
Retrofitting of homes in accordance with green design principles in five cities
Disseminating green building methods in local building
Creating a transition towards sustainable cities in Jordan, characterized by a low-carbon economy, a resilient infrastructure, and new green jobs in urban centers
Municipal solid waste management measures installed in Toqbol, Irbid, to mitigate methane emissions
Landfills rehabilitated to mitigate methane emissions
A new municipal solid waste landfill built in Ruweished
New waste compactors acquired
Climate Protection in the Waste Water Sector
Biogas production from municipal solid waste landfill in Tafeilah for electricity and/or thermal energy generation
Processing of manure collected from commercial farms in Dhulail Municipality to generate compost and biogas
Treatment of wastewater coupled with biogas production for energy generation at Dhulail Municipality
Capacity to mitigate black carbon (BC) emissions enhanced
Application of green building codes demonstrated in public and private buildings
Development of two city NAMAs including investment plan for existing and new buildings and street lighting
identification and quantification of the effectiveness of different policy and financial de-risking instruments for EE buildings using UNDP’s de-risking methodology
Green retrofit of main GAM buildig and City Hall
Capacity of GAM staff in green building design, operation, and maintenance developed
Demonstration of sustainable site planning and management of mixed use development promoting interconnected green space, multi-modal transportation, and clean construction
Walkability promoted in Amman
Traffic congestion reduced
Public health improved
Expanded MSW disposal capacity at Ghabawi landfill
Rehabilitating and upgrading biogas collection system in Ghabawi landfill
Upgrade of Ain Ghazal solid waste transfer station
Upgrade of Al-Shaer solid waste transfer station
| Impacts of energy efficiency & renewable energy deployments measured and verified | Development and Implementation of the Monitoring reporting and verification system, completed
Participation rates in JREEEF renewable energy and energy efficiency funding programs increased
Industrial SMEs certified in ISO 50001
Energy management training delivered to municipality managers
Adoption of energy efficiency measures and renewable energy systems by municipal managers
Feasibility study (technical and economic) for utilizing geothermal energy for heating and cooling purposes for different sectors completed
Feasibility study of recycling food waste effluents generated by food manufacturers conducted
Feasibility of biogas production from municipal solid waste landfill in Tafeilah for energy generation conducted
Feasibility of processing manure collected from commercial farms in Dhulail Municipality to generate compost and biogas conducted
Feasibility of treating wastewater coupled with biogas production for energy generation at Dhulail Municipality conducted
Renewable energy assessments conducted for SMEs
National Environmental Impact Assessment (EIA) of switching from diesel fuel to natural gas (NG) conducted
Feasibility study of solar wall technology for industrial applications at SMEs conducted
Awareness of RE & EE applications & benefits targeting industrial SMEs raised
Energy managers at industrial SMEs qualified for certification in energy management
Faster adoption of EE & RE measures at industrial SMEs
General student population informed about climate change mitigation and adaptation action
Capacity of education sector to address climate change raised
2. Adaptation to climate change strengthened in the water and agricultural sectors | Municipal water distribution network in Ayna, Karak Governorate, rehabilitated
Municipal water distribution network in Faqou'a, Karak Governorate, rehabilitated
Irrigation distribution network in Northern section of the Al-Aghwar rehabilitated
Irrigation distribution network in the mid section of Al-Aghwar rehabilitated
Irrigation distribution network in the Northeastern section of Al-Aghwar rehabilitated
Increased capacity in Balqa'a Governorate to collect and treat wastewater in a region that is not servced with water sanitation services
Expansion of Wadi Hassan WWTP and wastewater network serving municipality of Al-Jnaid and North Jarash
Construction of WWTP and wastewater network serving district of Al-Koura
Expansion of Al-Ramtha WWTP and wastewater network serving municipality of Sahl Houran and city of Al-Ramtha
Construction of wastewater networks in Naour
Construction of wastewater networks in Madaba
Construction of wastewater networks in Al-Azraq
Construction of wastewater networks in South Amman
Construction of wastewater networks in Ma'an
Construction of wastewater networks in Al-Karak
Construction of wastewater networks in Dhulail, Hallabat, and Khaldiah
Construction of wastewater networks in Al-jbarat, Al-Manarah, and other areas in Jarash
Expansion of Khirbat As-Samra WWTP (phase 3)
Increased capacity to collect and treat wastewater in the Jordan Valley
Water harvesting (capture and storage) projects implemented in the Badia
Capacity of MOA staff to plan for climate change adaptation strengthened
Grazing reserves by water harvesting sites established & rehabilitated
Ecosystem services restored and sustainably managed
Livelihood activities diversified & poverty reduced in Badia
Agricultural Risk Management To reduce frost effects
Reduce soil erosion through the management and harvesting of rainwater amongst small farmers in rural areas in Jordan
Strengthening the capability of the private sector on marketing the agricultural products (Marketing services companies).
Rehabilitation of rangeland reserves implemented
Water harvesting systems designed & built
Hima system for rangeland management implemented
Community participation in rangeland management implemented
Ecosystem services restored and sustainably managed
Water harvesting techniques introduced in rangeland
Forestation of recreational parks
Mitigating soil erosion
Creating jobs for low-income families tending ther parks
Water irrigation channels upgraded & maintained
Springs and water sources protected from pollution
Income & resilience of poor families in rural areas and Badia improved by providing a package of free livestock and skills training
New jobs created through green works in agriculture and forestry
Workers acquiring skills in forestation, terrace building, drip irrigation, cistern construction, and seedling production
Assessment of the impact of climate change on water productivity of rainfed and irrigated crops in three regions (north, middle, and south) of Jordan
| Land reclamation implemented | No. of new jobs created are 1300 by IFAD
Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi, Technical assistance and financial incentives to farmers; ( $1,268,508 loans to SMEs + 204 people accessing rural finance (108 women) + 1 policy knowledge product).
No. of training workshops/No. of farmers trained are 1612 (583 women)
Supplementary irrigation of rainfed olive trees implemented
Yield of rainfed olive trees increased
Organic agriculture methods introduced
Contract farming introduced
Resiliency of small farmers and rural women strengthened
School children trained to plant, care for, and harvest olive trees in their schools using treated greywater
Mainstreaming use of treated greywater for irrigation
Domestic/small scale aquaponics production units installed
Economic empowerment of rural women
Enhancing skills of rural women in food production & marketing
Enhancing livelihood of rural women and their families
Home gardens promoted
Household food security achieved
Agricultural associations activated
Improving productivity of farmers thru mechanized farming
Area of cultivation expanded - Reduction in harvest loss
New jobs created
Capacity of recent university graduates and the unemployed enhanced thru training and establishment of hydroponics and aquaponics incubators
Re-settlement of date palm trees in Al-Azraq ecosystem
Income-generating activities for rural communities supported
Green cover deterioration and desertification risk mitigated
| Increasing the resilience of displaced persons to climate change-related water challenges in urban host settlements | The Adaptation Fund has approved financing their proposal titled “Increasing the Resilience of both Displaced Persons and Host Communities to Climate Change-Related Water Challenges in Jordan and Lebanon” with grant 14MUS$. |  | The Adaptation Fund has approved financing their proposal titled “Increasing the Resilience of both Displaced Persons and Host Communities to Climate Change-Related Water Challenges in Jordan and Lebanon” with grant 14MUS$.
Enhancing community resilience by building a 100 Km green belt and launching ecosystem-based enterprises inside forested areas located east of Amman and Zarqa at the desert edge
Sustainable recreational parks developed and managed by community-based organizations (CBOs) in each Governorate
Enhancing the capacity to store water and provide cash by building 500 water cisterns
Conservation of local landraces
Strengthening resilience of ecosystems to climate change stresses
Enhanced adaptive capacity & income for small farmers
Prioritized adaptation practices implemented
Efficient planning & use of resources & enhancing productivity
Increased farm income & investment in CC adaptation
Identification of suitable water harvesting sites in Badia
Scenarios developed for applying water harvesting techniques
Rehabilitated vegetation cover and pastures
Conceptual framework combining silvicultural, ecological and community-based approaches for afforestation & honeybee foraging
Developing new knowledge-based policy for afforestation
Selecting new varieties of wheat with increased salinity tolerance
Wheat cultivation expanded to new areas
Sustainable, participatory roadside afforestation implemented
Reduced poverty by providing afforestation jobs
Improved ecosystems and enhanced biodiversity
Building gardens in public schools using permaculture
Introducing permaculture in vocational education courses
Students awareness of land, wild outdoors, and health raised
Risks of climate change on epidemiology of plant pests assessed
Farmers and extension agents awareness of new pests and control measures developed
Scaling up cultivation of quinoa as an adaptation action
Improved food and nutritional security in poor communities
Crop modeling framework to improve management of cropping systems and provide farmers with CC adaptive measures
Exploration of crop scenarios facilitated using expert system
Dissemination of conservation agriculture to increase wheat and barley production in dry areas using improved varieties
Enhancing food security under climate change scenarios
Development of high efficiency gray water treatment system using coagulation and flocculation materials extracted from plants
Development of gray water treatment system using shredded tire as bio-filter
Treatment of gray water and re-use demonstrated
Scale-up of gray water treatment and reuse in home garden irrigation using findings from NARC development studies/projects
Land use change mapped in Amman (1984 to 2018) using GIS and remote sensing methods to detect changes in vegetation cover
Awareness of impact of urbanization on agricultural land raised
Improving rural livelihood by developing Carob cultivars
Diversified farm income and enhanced resiliency
Improved field pest control using sustainable pest management
Enhanced adaptive capacity and resiliency of plants
Method to detoxify olive oil mill wastewater demonstrated
Environmental chemistry lab established for pollutant detection
Protecting ecosystems and water resources from OMW pollution
Integrating climate change adaptation and mitigation into the watershed management plan of Wadi Shouib
Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi
| Sustainable land use planning to improve land productivity and increase ecosystem integrity | Agreement signed with the Inter-Islamic Network for Water Resources Development and Management (INWRDAM) and implementation has been initiated
Appropriate adaptation interventions identified to restore degraded lands and rangelands and improve resiliency to drought
A revolving loan fund for supporting climate change mitigation and adaptation action by farmers created
Strengthening institutional capacity of Jordan Environmental Fund (JEF) to enhance ability of JEF beneficiaries (NGOs & public sector actors) to implement CC mitigation and adaptation actions
M&E and data analysis for water (focus on water for agricultural use) and waste (focus on solid waste) sectors
Feasibility study of rehabilitating irrigation distribution network in the Northern section of the Al-Aghwar conducted
Feasibility study of rehabilitating irrigation distribution network in the mid section of Al-Aghwar conducted
Feasibility study of rehabilitating irrigation distribution network in the Northeastern section of Al-Aghwar conducted
Feasibility study of introducing SCADA system in Southern region of Jordan Valley conducted
Wadi Nkhail dam project feasibility study conducted
Technical study of the Tilal Dhahab dam project conducted
Feasibility Study to reduce water losses and increase water savings in the northern part of King Abdullah Canal
Feasibility study on the transfer of treated wastewater from the South Amman wastewater Treatment plant to the Wadi Husban dam and conveyance to the King Abdullah Canal
3. Adaptation to climate change strengthened in multiple sectors (ecosystems, gender-based resiliency, health, local governance, social conditions, etc.) | An assessment of the relative benefits of the 35 individual NDC actions for reducing GHG emissions (i.e. mitigation) and reducing potential climate impacts (i.e. adaptation) versus their cost.
Improved conservation status of climate vulnerable ecosystems and strengthened adaptive capacities of key ecological hotspots
Conservation plan for climate vulnerable ecosystems updated and network of protected areas (PAs), revised PA buffer zones, and spacial conservation areas (SCAs) officially established
| Enhanced capacities to develop mitigation and adaptation plans | The second Biennial Update Report has been finalized and under revision, expected submission date end of Nov. 2020
Technical assistance task for the Southern Neighborhood region, including Jordan, to enhance municipalities to develop sustainable energy and climate action plans, to support climate action
| Increased number of local sustainable actions (SEACAPs) | 1. Development of a detailed methodology for NDC revision to be approved and verified by stakeholders 2. Training for national partners in data management for GHG Emissions inventory and calculations 3. Developing three local climate action plans (LCAPs) for the first time in Jordan and supporting the implementation of one pilot measure.
| assessment of the potential sources of financing for the prioritised options | Amman Climate Plan Financing strategy
| Improved access to financing mechanisms | Design of the digital finance platform with Development of business case for digital finance platform with JOPACC and Development of Green Bonds guidelines • Ricardo has received most data needed and will now begin to analyze and form initial reviews. • The main issue to be raised is that Ricardo has reached out to partners to cross-check cost and benefit information to make sure it is in line. o More inputs on benefit quantification would be helpful, either from experience of Jordan or in the region
Enhanced capacities in Aqaba Special Economic Zone Authority (ASEZA) to develop mitigation and adaptation plans
Health sector preparedness strengthened
Surveillance system for climate change sensitive diseases established in 15 sentinel hospitals and 20 health centers
Surveillance system for occupational climate change sensitive diseases established
Leishmania Unit in Division of Parasitic and Zoonotic Diseases established
Enhancing income of rural families falling below the poverty line
New jobs created
Improved development services in local community
Income and agricultural productivity projects targeting poor rural households expanded
Income diversification for rural households
Enhancing capacity of MoSD staff to design and deliver climate resilient services to women and the poor
Raising awareness of MoSD staff of climate change risks & actions
Enhancing leadershjp capacity of community-based groups (CBOs) to address climate change
Raising women's awareness of climate change risks & actions
Contribution of non-governmental actors in ASEZA to support NDC implementation increased
Capacities of non-governmental actors in ASEZA to conduct climate change research enhanced
Blue Economy Principles for Improved Touristic Competitiveness, Livelihoods of the Fishermen Community, Industrial Development and Monitoring Indicators of Pollution Control and Climate Change in the Jordanian Sector of the Gulf of Aqaba, Red Sea

## Focal Points
Name of Institution | Name of Focal Point | Title | E-mail Address
Jordan Renewable Energy and Energy Efficiency Fund (JREEEF) | Lina Al-Mobaideen | Project Development Manager | Lina.Mobaideen@memr.gov.jo
| Ola Al-Sarhan | Acting Head of Technical Assistance Section | Ola.Alsarhan@memr.gov.jo
Ministry of Energy and Mineral Resources (MEMR) | Yacoub Elias Marar | Director of Renewable Energy Department | Yacoub.marar@memr.gov.jo
National Electric Power Company (NEPCO) | Ahmed Aldohni | Section Head, Contracts & Agreements | adohni@nepco.com.jo
Ministry of Water and Irrigation (MWI) | Thaer Al-Momani | Director, Env & Climate Change Directorate | Thair_Almomani@mwi.gov.jo
| Basim Hasan | Strategic Planning Specialist | basim_Hasan@mwi.gov.jo
| Wafa Shehadeh | Head of Energy Efficiency Division | Wafa_Shehadeh@mwi.gov.jo
| Zaineb Abu Zaid | Head of Regional Water Division, JVA | zaineb_abuzaid@mwi.gov.jo
| Naimeh S. Ibsieleh | Head of Strategic Planning Department, WAJ | Naimeh_Ibsieleh@mwi.gov.jo
Ministry of Agriculture (MOA) | Mohammad El-Shebli | Head, Climate Change Department | Mohammad.elshebli@moa.gov.jo
| Hiba Al-Kharabsheh | Researcher, Climate Change Directorate (NARC) | hibamsus@gmail.com
Ministry of Transportation (MOT) | Majdi Abu-Hammoudeh | Director, Transport Safety Directorate | Majdi.Abuhammoudeh@mot.gov.jo
| Obadah Abu-Qamar | Mechanical Engineer, Directorate of Studies (LTRC) | obadah.abuqamar@ltrc.gov.jo
Ministry of Municipal Affairs (MOMA) | Hussain Al-Mhaidat | Advisor to Minister for SWM | hussain_mhaidat@yahoo.com
| Rushdi Alsheikh | Climate Change Coordinator | rushdi_87@yahoo.com
| Hamza Al-Mherat | Senior Engineer | eng.hamzaabbadi@yahoo.com
Ministry of Health (MOH) | Sami Sheikh Ali | Head, Data Management Department | saadshali@hotmail.com
Ministry of Social Development (MoSD) | Kahraman Adnan | Director, Productivity Enhancement Directorate | kahraman.abdallah@mosd.gov.jo
| Ola Arafat | Department Head, Housing | ola.arafat@yahoo.com
Ministry of Environment (MoEnv) | Belal Shaqarin | Director, Climate Change Directorate | shqareen@yahoo.com
| Eng. Ahmad Al Qatarneh | Secretary General
Ministry of Planning and International Cooperation (MOPIC) | Wa'ed Ja'afreh | Project Engineer | waed.al-jaafreh@mop.gov.jo
| Zeina Toukan | Secretary General
Greater Amman Municipality (GAM) | Nisreen Alaraj | Mayor’s Advisor for Projects | Nisreen.Alaraj@ammancity.gov.jo
Jordan Environment Fund (JEF) | Eng. Ahmad Al Qatarneh | Secretary General
Royal Society for the Conservation of Nature (RSCN) | Maen Smadi | Director of Protected Areas | maen@rscn.org.jo
The Royal Marine Conservation Society of Jordan (JREDS) | Ehab Eid | Executive Director | e.eid@jreds.org
Jordan Chamber of Industry (JCI) | Maen Ali Ayasrah | Coordinator of Energy Unit & Environment | maen@jci.org.jo
Jordan Green Building Council (JGBC) | Ala’a Abdullah | Executive Director | Alaa.abdullah@jordangbc.org

## Drop-down menu
Policy, Strategy and Legislative Services | Status
NDC prioritization exercise | Ongoing
NDC gap analysis | Planned
NDC implementation road maps/timelines | Concluded
Alignment of NDCs with SDGs | Indicative
Long term climate strategies and vision | Without support
NDC mainstreaming at the national and subnational level
NDC revision
Legal framework
Policy analysis/support (cost-benefit analysis; vulnerability assessments)
Status of fiscal policy/market readiness
Governance and coordination mechanisms
Budgeting and Investment Services
Fiscal and macro-economic projections
Costing commitments and implementation pathways of NDCs
MTEF, Public Investment Programming, Investment plans (needs vs. availability of resources)
Developing pipelines of Bbankable projects
Climate change fund establishment
Raising/combining climate finance
Blending/delivering climate finance
Private sector investments mobilization
Up-scaling business solutions
Partnering with cornerstone investors
Monitoring and Evaluation (M&E) Services
Data gap analysis
M&E frameworks/Results Chains
Setting indicators and targets
Data collection and management
MRV of emissions
MRV of mitigation actions
MRV of financial and technical support
Capacity Building and Lessons Learning
Training needs in any of the other areas/sections
Feasibility studies (social, technical, economic)
Human capacity increase
Tools/guidelines
South-South learning
Knowledge-sharing
Communications
Cross-cutting/Others (Specify)

## amendent from C to D
Organic agriculture methods introduced | Develop models on use of organic waste at Zatari refugee camp to covert to composting, and use sludge from waste water treatment and organic waste to pilot a waste to energy project producing biogas and electricity in Zatari refugee camp | 283 | 272
New jobs created | No. of new jobs created are 1300 by IFAD | 300 | 278
Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi | Guidance and tools developed to support SMEs go green and help youth sustain agricultural activities in the wadi, Technical assistance and financial incentives to farmers; ( $1,268,508 loans to SMEs + 204 people accessing rural finance (108 women) + 1 policy knowledge product). | 375 | 277
Raising women's awareness of climate change risks & actions | No. of training workshops/No. of farmers trained are 1612 (583 women) | 450 | 277